## निर्देश (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
मानदंड और सदस्य परिभाषित करें | चेकलिस्ट आइटम पंजीकृत करें | सत्यापन और मंज़ूरी दर्ज करें | GO / NO-GO को अंतिम रूप दें
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## डैशबोर्ड (dashboard)
डैशबोर्ड (dashboard)
Excel template for product management release readiness checklist template.
Category | कार्य | Completed Tasks | पूर्णता दर
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## चेकलिस्ट (रजिस्टर)
चेकलिस्ट (रजिस्टर)
Excel template for product management release readiness checklist template.
Item ID | Checklist Item | Category | स्थिति | गंभीरता | स्वामी | हिंदी: Reviewer | नियत तिथि | जांच तिथि | Evidence | नोट्स
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | स्थिति | आवश्यक | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Pending | आवश्यक | SRE Lead | Client Interface Fields Not Confirmed | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | रुका हुआ | अनुशंसा | Support lead | Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## मंज़ूरी इतिहास (लॉग)
मंज़ूरी इतिहास (लॉग)
Excel template for product management release readiness checklist template.
मंज़ूरी आईडी | Department/role | मंज़ूरीकर्ता का नाम | Disposition result | अनुमोदन तिथि | मंज़ूरीकर्ता की टिप्पणियाँ और सत्यापन बिंदु
Sign-001 | उत्पाद विभाग | Product owner | शर्तों के साथ GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | इंजीनियरिंग विभाग | Client Interface Fields Not Confirmed | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | इन्फ्रास्ट्रक्चर और SRE विभाग | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## मानदंड सेटिंग्स (सेटिंग्स)
मानदंड सेटिंग्स (सेटिंग्स)
Excel template for product management release readiness checklist template.
निर्णय श्रेणियाँ | रिलीज़ निर्णय सदस्य | Department/role | Statuses | Importance Master
1. Development & QA | Member 1 | उत्पाद विभाग | Pending | आवश्यक
2. Infrastructure & Operations | Member 2 | इंजीनियरिंग विभाग | Pending | अनुशंसा
3. Sales & Customer Support | Product owner | इन्फ्रास्ट्रक्चर और SRE विभाग | स्थिति | Optional