## Instruksi (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
LANGKAH 1 | LANGKAH 2 | LANGKAH 3 | LANGKAH 4
Definisikan Kriteria & Anggota | Daftarkan Item Kuesioner | Catat Verifikasi & Persetujuan | Finalisasi GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Coding Guide)

## Dasbor (dashboard)
Dasbor (dashboard)
Excel template for product management release readiness checklist template.
Kategori | Tugas | Tugas Selesai | Tingkat penyelesaian
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Kuesioner (register)
Kuesioner (register)
Excel template for product management release readiness checklist template.
Item ID | Check item | Kategori | Respons atau Catatan | Fitur utama | Batas pengecekan | Pemeriksa | Target tanggal | Column9 | Evidence | Catatan
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Status | Wajib | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Menunggu | Wajib | SRE Lead | Client Interface Fields Not Confirmed | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Proyek konstruksi pusat | Recommended | Support lead | Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Riwayat Persetujuan (log)
Riwayat Persetujuan (log)
Excel template for product management release readiness checklist template.
ID Persetujuan | Department/role | Nama Pemberi Persetujuan | Hasil keputusan | Tanggal persetujuan | Komentar & Poin Verifikasi Pemberi Persetujuan
Sign-001 | Departemen Produk | Product owner | Syarat GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Departemen Teknik | Client Interface Fields Not Confirmed | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Departemen Infrastruktur & SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Pengaturan Kriteria (settings)
Pengaturan Kriteria (settings)
Excel template for product management release readiness checklist template.
Kategori Keputusan | Anggota Keputusan Rilis | Department/role | Statuses | Importance Master
1. Development & QA | Member 1 | Departemen Produk | Belum diperiksa | Wajib
2. Infrastructure & Operations | Member 2 | Departemen Teknik | Menunggu | Recommended
3. Sales & Customer Support | Product owner | Departemen Infrastruktur & SRE | Status | Opsional