## Leiðbeiningar (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Skilgreina viðmið og meðlimi | Skrá á vigtarlista atriði | Staðfesta og samþykkja skráningar | Lokaðu GO / NO-GO ákvörðun
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Mælaborð (dashboard)
Mælaborð (dashboard)
Excel template for product management release readiness checklist template.
Category | Verkefni | Completed Tasks | Lokahlutfall
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Vigtarlisti (skráning)
Vigtarlisti (skráning)
Excel template for product management release readiness checklist template.
Atriðis-ID | Skoðunaratriði | Category | Staða | Alvarleiki | Ábyrgðaraðili | Yfirferðaraðili | Eindagi | Skoðunardagur | Evidence | Athugasemdir
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Lokið | Nauðsynlegt | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Í staðfestingu | Nauðsynlegt | SRE Lead | Tæknilegur ábyrgðaraðili | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Í bið | Ráðlegging | Stuðningsleiðtogi | Vöruábyrgðaraðili | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Samþykkissaga (skrá)
Samþykkissaga (skrá)
Excel template for product management release readiness checklist template.
Samþykkisauðkenni | Deild/hlutverk | Nafn samþykktaraðila | Ráðstöfunarniðurstaða | Samþykktardagsetning | Athugasemdir samþykktaraðila og staðfestingarpunktar
Sign-001 | Vörudeild | Vöruábyrgðaraðili | Tilboðs samþykkt | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Verkfræðideild | Tæknilegur ábyrgðaraðili | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Deild innviða og SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Stillingar viðmiða (stillingar)
Stillingar viðmiða (stillingar)
Excel template for product management release readiness checklist template.
Ákvörðunarflokkar | Meðlimir ákvörðunar um útgáfu | Deild/hlutverk | Stöðuskrá | Importance Master
1. Development & QA | Member 1 | Vörudeild | Ekki yfirfarið | Nauðsynlegt
2. Infrastructure & Operations | Member 2 | Verkfræðideild | Í staðfestingu | Ráðlegging
3. Sales & Customer Support | Vöruábyrgðaraðili | Deild innviða og SRE | Lokið | Valfrjálst