## ຄຳແນະນຳ (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
ກຳ​ນົດ​ເງື່ອນ​ໄຂ​ & ສະ​ມາ​ຊິກ | ລົງ​ທະ​ບຽນ​ລາຍການ​ກວດ​ສອບ | ບັນ​ທຶກ​ການ​ກວດ​ສອບ​ & ການ​ອະ​ນຸ​ມັດ | ສຸດ​ທ້າຍ​ GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## ແດຊບອດ (dashboard)
ແດຊບອດ (dashboard)
Excel template for product management release readiness checklist template.
Category | ວຽກ | Completed Tasks | ອັດຕາເສຣັຈສິ້ນ
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## ລາຍ​ການ​ກວດ​ສອບ (register)
ລາຍ​ການ​ກວດ​ສອບ (register)
Excel template for product management release readiness checklist template.
ຣະເບີຍນ Item-ID | ຣະເບີຍນ Check item | Category | ສະຖານະ | ລະດັບຄວາມຣຸນແຣງ | ຜູ້ຣັບຜິດຊອບ | ຄ່າໄທຍສຳລັບ Reviewer | ວັນທີ່ຄຣບກຳຫນດ | ວັນທີ່ຂອ | Evidence | ຫມາຍເຫຕຸ
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | ເສຣັຈສິ້ນ | ຄ່າໄທຍສຳລັບ Required | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | ຣະເບີຍນ Verifying | ຄ່າໄທຍສຳລັບ Required | SRE Lead | ຜູ້ປຣະສານວຽກ | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | ຢຸດຊັ່ວຄຣາວແລ້ວ | ຄໍາແນະນໍາ | ຣະເບີຍນ Support lead | ຣະເບີຍນ Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## ປະ​ຫວັດ​ການ​ອະ​ນຸ​ມັດ (log)
ປະ​ຫວັດ​ການ​ອະ​ນຸ​ມັດ (log)
Excel template for product management release readiness checklist template.
ID ​ການ​ອະ​ນຸ​ມັດ | ຣະເບີຍນ Department/role | ຊື່​ຜູ້​ອະ​ນຸ​ມັດ | ການຕັດສິນ | ວັນທີອະນຸມັດ | ຄຳ​ເຫັນ​ຂອງ​ຜູ້​ອະ​ນຸ​ມັດ & ຈຸດ​ກວດ​ສອບ
Sign-001 | ພະ​ແນກ​ຜະລິດຕະພັນ | ຣະເບີຍນ Product owner | Conditional GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | ພະ​ແນກ​ວິ​ສະ​ວະ​ກຳ | ຜູ້ປຣະສານວຽກ | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | ພະ​ແນກ​ໂຄງ​ລ່າງ & SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## ການ​ຕັ້ງ​ຄ່າ​ເງື່ອນ​ໄຂ (setting
ການ​ຕັ້ງ​ຄ່າ​ເງື່ອນ​ໄຂ (setting
Excel template for product management release readiness checklist template.
ປະ​ເພດ​ການ​ຕັດ​ສິນ | ສະ​ມາ​ຊິກ​ການ​ຕັດ​ສິນ​ການ​ປ່ອຍ | ຣະເບີຍນ Department/role | Statuses | Importance Master
1. Development & QA | Member 1 | ພະ​ແນກ​ຜະລິດຕະພັນ | ລາຍການ | ຄ່າໄທຍສຳລັບ Required
2. Infrastructure & Operations | Member 2 | ພະ​ແນກ​ວິ​ສະ​ວະ​ກຳ | ຣະເບີຍນ Verifying | ຄໍາແນະນໍາ
3. Sales & Customer Support | ຣະເບີຍນ Product owner | ພະ​ແນກ​ໂຄງ​ລ່າງ & SRE | ເສຣັຈສິ້ນ | ໄມ່ບັງຄັບ