## सूचना (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
निकष आणि सदस्य परिभाषित करा | चेकलिस्ट आयटम्स नोंदवा | पडताळणी आणि मंजूरीची नोंद करा | GO / NO-GO अंतिम करा
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## डॅशबोर्ड (dashboard)
डॅशबोर्ड (dashboard)
Excel template for product management release readiness checklist template.
Category | कार्य | Completed Tasks | कार्य माहिती
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## चेकलिस्ट (नोंदणी)
चेकलिस्ट (नोंदणी)
Excel template for product management release readiness checklist template.
फील्ड | Column2 | Category | स्थिती | कार्य माहिती | मालक | Reviewer | Column8 | Column9 | Evidence | टीप
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | पूर्ण | आवश्यक | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | कार्य माहिती | आवश्यक | SRE Lead | फील्ड | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | कार्य माहिती | फील्ड | समर्थन लीड | कार्य माहिती | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## मंजुरी इतिहास (लॉग)
मंजुरी इतिहास (लॉग)
Excel template for product management release readiness checklist template.
मंजुरी आयडी | फील्ड | मंजुरी देणाऱ्याचे नाव | कार्य माहिती | Approval Date | मंजुरी देणाऱ्याच्या टिप्पण्या आणि पडताळणी मुद्दे
Sign-001 | उत्पादन विभाग | कार्य माहिती | अटींसह GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | अभियांत्रिकी विभाग | फील्ड | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | इन्फ्रास्ट्रक्चर आणि SRE विभाग | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## निकष सेटिंग्ज (सेटिंग्ज)
निकष सेटिंग्ज (सेटिंग्ज)
Excel template for product management release readiness checklist template.
निर्णय श्रेण्या | रिलीज निर्णय सदस्य | फील्ड | स्थिती शब्दकोश | Importance Master
1. Development & QA | Member 1 | उत्पादन विभाग | कार्य माहिती | आवश्यक
2. Infrastructure & Operations | Member 2 | अभियांत्रिकी विभाग | कार्य माहिती | फील्ड
3. Sales & Customer Support | कार्य माहिती | इन्फ्रास्ट्रक्चर आणि SRE विभाग | पूर्ण | कार्य माहिती