## Instrucțiuni (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Definire Criterii & Membri | Înregistrare Articole din Lista de Verificare | Înregistrare Verificare & Aprobare | Finalizare GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Tablou de bord (dashboard)
Tablou de bord (dashboard)
Excel template for product management release readiness checklist template.
Category | Sarcină | Completed Tasks | Rată de finalizare
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Lista de Verificare (înregistra
Lista de Verificare (înregistra
Excel template for product management release readiness checklist template.
ID element | de verificat | Category | Stare | severitate | Responsabil | Revizor | Termen limită | Data verificării | Evidence | Note
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Finalizat | Necesar | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Verifying | Necesar | SRE Lead | Responsabil tehnic | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Pauzăd | Recomandare | Coordonator suport | Responsabil produs | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Istoric Aprobări (log)
Istoric Aprobări (log)
Excel template for product management release readiness checklist template.
ID Aprobare | Department/role | Nume Aprobator | Rezultat dispoziție | Data aprobării | Comentarii Aprobator & Puncte de Verificare
Sign-001 | Departament Produs | Responsabil produs | GO Condiționat | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Departament Inginerie | Responsabil tehnic | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Departament Infrastructură & SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Setări Criterii (setări)
Setări Criterii (setări)
Excel template for product management release readiness checklist template.
Categorii de Decizie | Membri ai Echipei de Decizie pentru Lansare | Department/role | Status Dictionary | Importance Master
1. Development & QA | Member 1 | Departament Produs | Element | Necesar
2. Infrastructure & Operations | Member 2 | Departament Inginerie | Verifying | Recomandare
3. Sales & Customer Support | Responsabil produs | Departament Infrastructură & SRE | Finalizat | Opțional