## Pokyny (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Definovať kritériá a členov | Zaregistrovať položky kontrolného zoznamu | Záznam overenia a schválenia | Finalizovať GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Riadiaci panel (dashboard)
Riadiaci panel (dashboard)
Excel template for product management release readiness checklist template.
Category | Úloha | Completed Tasks | Miera dokončenia
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Kontrolný zoznam (register)
Kontrolný zoznam (register)
Excel template for product management release readiness checklist template.
Záznam Item-ID | Položka kontroly | Category | Stav | Závažnosť | Vlastník | Kontrolór | Termín | Dátum kontroly | Evidence | Poznámky
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Dokončené | Použite ho, keď potrebujete centralizovať sledovanie. | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Záznam Verifying | Použite ho, keď potrebujete centralizovať sledovanie. | SRE Lead | Zodpovedný | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Pozastavené | Odporúčanie | Záznam Support lead | Záznam Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## História schválenia (denník)
História schválenia (denník)
Excel template for product management release readiness checklist template.
ID schválenia | Záznam Department/role | Meno schvaľovateľa | Výsledok dispozície | Approval Date | Komentáre schvaľovateľa a body overenia
Sign-001 | Produktové oddelenie | Záznam Product owner | Podmienené GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Inžinierske oddelenie | Zodpovedný | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Oddelenie infraštruktúry a SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Nastavenia kritérií (nastavenia
Nastavenia kritérií (nastavenia
Excel template for product management release readiness checklist template.
Kategórie rozhodnutí | Členovia rozhodovania o vydaní | Záznam Department/role | Status Dictionary | Importance Master
1. Development & QA | Member 1 | Produktové oddelenie | Polozka | Použite ho, keď potrebujete centralizovať sledovanie.
2. Infrastructure & Operations | Member 2 | Inžinierske oddelenie | Záznam Verifying | Odporúčanie
3. Sales & Customer Support | Záznam Product owner | Oddelenie infraštruktúry a SRE | Dokončené | Voliteľné