## Упутство (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Definiši kriterijume i članove | Registruj stavke na kontrolnoj listi | Evidentiraj verifikaciju i odobrenje | Donesi konačnu odluku GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Контролна табла (dashboard)
Контролна табла (dashboard)
Excel template for product management release readiness checklist template.
Category | Zadatak | Completed Tasks | Stopa dopune
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Kontrolna lista (registar)
Kontrolna lista (registar)
Excel template for product management release readiness checklist template.
Item ID | Stavka pregleda | Category | Stanje | Ozbiljnost | Odgovorni | Pregledavatelj | Ciljni datum | Datum provjere | Evidence | Napomene
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Gotovo | Zahtev | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | U pregledu | Zahtev | SRE Lead | Polja sučelja klijenta nisu potvrđena | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Izvestilac | Preporuka | Voditelj podrške | Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Istorija odobrenja (log)
Istorija odobrenja (log)
Excel template for product management release readiness checklist template.
ID odobrenja | Department/role | Ime odobravaoca | Rezultat odluke | Approval date | Komentari odobravaoca i tačke provere
Sign-001 | Odeljenje za proizvode | Product owner | Uslovno GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Inženjersko odeljenje | Polja sučelja klijenta nisu potvrđena | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Odeljenje za infrastrukturu i SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Podešavanja kriterijuma (podeša
Podešavanja kriterijuma (podeša
Excel template for product management release readiness checklist template.
Kategorije odluka | Članovi tima za odluku o izdanju | Department/role | Statuses | Importance Master
1. Development & QA | Member 1 | Odeljenje za proizvode | Na cekanju | Zahtev
2. Infrastructure & Operations | Member 2 | Inženjersko odeljenje | U pregledu | Preporuka
3. Sales & Customer Support | Product owner | Odeljenje za infrastrukturu i SRE | Gotovo | Opciono