## Instruktioner (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Definiera kriterier och medlemmar | Registrera checklisteposter | Registrera verifiering och godkännande | Slutför GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Instrumentpanel (dashboard)
Instrumentpanel (dashboard)
Excel template for product management release readiness checklist template.
Category | Uppgift | Completed Tasks | Slutförandegrad
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Checklista (register)
Checklista (register)
Excel template for product management release readiness checklist template.
Post Item-ID | Post Check item | Category | Status | Allvarlighetsgrad | Ägare | Granskare | Förfallodag | Kontrolldatum | Evidence | Anteckningar
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Slutförd | Krävs | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Post Verifying | Krävs | SRE Lead | Post Technical owner | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Pausad | Rekommendation | Post Support lead | Post Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Godkännandehistorik (logg)
Godkännandehistorik (logg)
Excel template for product management release readiness checklist template.
Godkännande-ID | Post Department/role | Godkännarens namn | Dispositionsresultat | Approval Date | Godkännarkommentarer och verifieringspunkter
Sign-001 | Produktavdelning | Post Product owner | Villkorligt GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Teknikavdelning | Post Technical owner | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Avdelningen för infrastruktur och SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Kriterieinställningar (inställn
Kriterieinställningar (inställn
Excel template for product management release readiness checklist template.
Beslutskategorier | Medlemmar i releasebeslut | Post Department/role | Status Dictionary | Importance Master
1. Development & QA | Member 1 | Produktavdelning | Objekt | Krävs
2. Infrastructure & Operations | Member 2 | Teknikavdelning | Post Verifying | Rekommendation
3. Sales & Customer Support | Post Product owner | Avdelningen för infrastruktur och SRE | Slutförd | Valfri anteckning