## Maagizo (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Fafanua Vigezo na Wanachama | Sajili Vipengele vya Orodha | Rekodi Uhakiki na Idhini | Maliza GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Dashibodi (dashboard)
Dashibodi (dashboard)
Excel template for product management release readiness checklist template.
Category | Kazi | Completed Tasks | Kiwango cha kukamilika
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Orodha (sajili)
Orodha (sajili)
Excel template for product management release readiness checklist template.
Rekodi Item-ID | Kipengee cha ukaguzi | Category | Hali | Ukosefu wa Haki | Mhusika | Mkaguzi | Tarehe ya kukamilika | Check date | Evidence | Maelezo
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Imekamilika | Zahitajiwa | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Rekodi Verifying | Zahitajiwa | SRE Lead | Rekodi Technical owner | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Paside | Pendekezo | Rekodi Support lead | Rekodi Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Historia ya Idhini (logi)
Historia ya Idhini (logi)
Excel template for product management release readiness checklist template.
Kitambulisho cha Idhini | Rekodi Department/role | Jina la Mthibitishaji | Matokeo ya uamuzi | Approval Date | Maoni ya Mthibitishaji na Vipengele vya Uhakiki
Sign-001 | Idara ya Bidhaa | Rekodi Product owner | GO ya Masharti | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Idara ya Uhandisi | Rekodi Technical owner | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Idara ya Miundombinu & SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Mipangilio ya Vigezo (mipangili
Mipangilio ya Vigezo (mipangili
Excel template for product management release readiness checklist template.
Kategoria za Uamuzi | Wanachama wa Uamuzi wa Kutolewa | Rekodi Department/role | Status Dictionary | Importance Master
1. Development & QA | Member 1 | Idara ya Bidhaa | Kipengee | Zahitajiwa
2. Infrastructure & Operations | Member 2 | Idara ya Uhandisi | Rekodi Verifying | Pendekezo
3. Sales & Customer Support | Rekodi Product owner | Idara ya Miundombinu & SRE | Imekamilika | Hiari