## Mga Instruksyon (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
Tukuyin ang mga Pamantayan at Miyembro | Irehistro ang mga Checklist Item | Itala ang Pag-verify at Pag-apruba | Tapusin ang GO / NO-GO
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## Dashboard (dashboard)
Dashboard (dashboard)
Excel template for product management release readiness checklist template.
Category | Gawain | Completed Tasks | Rate ng pagkumpleto
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## Checklist (rehistro)
Checklist (rehistro)
Excel template for product management release readiness checklist template.
Tala Item-ID | Tala Check item | Category | Status | Lalong-lala | May-ari | Tagalog: Reviewer | Tala Due date | Petsa ng check | Evidence | Mga tala
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | Nakumpleto | Tagalog: Required | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | Tala Verifying | Tagalog: Required | SRE Lead | Tala Technical owner | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | Naka-pause | Recommendation | Tala Support lead | Tala Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## Kasaysayan ng Pag-apruba (log)
Kasaysayan ng Pag-apruba (log)
Excel template for product management release readiness checklist template.
Approval ID | Tala Department/role | Pangalan ng Nag-apruba | Disposition Resulta | Approval Date | Mga Komento ng Nag-apruba at Mga Punto ng Pag-verify
Sign-001 | Departamento ng Produkto | Tala Product owner | Kondisyonal na GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | Departamento ng Inhinyeriya | Tala Technical owner | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | Departamento ng Impraestruktura at SRE | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## Pagtatakda ng mga Pamantayan (s
Pagtatakda ng mga Pamantayan (s
Excel template for product management release readiness checklist template.
Mga Kategorya ng Desisyon | Mga Miyembro ng Desisyon sa Paglabas | Tala Department/role | Status Dictionary | Importance Master
1. Development & QA | Member 1 | Departamento ng Produkto | Item | Tagalog: Required
2. Infrastructure & Operations | Member 2 | Departamento ng Inhinyeriya | Tala Verifying | Recommendation
3. Sales & Customer Support | Tala Product owner | Departamento ng Impraestruktura at SRE | Nakumpleto | Opsyonal