## ہدایات (instructions)
Product Management Release Readiness Checklist Template
Excel template for product management release readiness checklist template.
STEP 1 | STEP 2 | STEP 3 | STEP 4
معیارات اور ممبرز کی وضاحت کریں | چیک لسٹ آئٹمز کو رجسٹر کریں | توثیق اور منظوری کا ریکارڈ رکھیں | GO / NO-GO کو حتمی شکل دیں
In the "Criteria Settings" sheet, define the category for decisions (Development, Infrastructure, Sales, etc.), importance (Required, Recommended), and team members. | In the "Checklist" sheet, register requirement items to be confirmed before release for each department, along with importance and due dates. | Register verification results and completion status for each checklist item, and perform sign-offs (approvals) by related departments in the "Approval History" sheet. | In the "Dashboard" sheet, confirm the completion rate of required items and blocked issues to finalize the final decision.
Legend (Cell Color Guide)

## ڈیش بورڈ (dashboard)
ڈیش بورڈ (dashboard)
Excel template for product management release readiness checklist template.
Category | کام | Completed Tasks | completion rate
1. Development & QA
2. Infrastructure & Operations
3. Sales & Customer Support

## چیک لسٹ (رجسٹر)
چیک لسٹ (رجسٹر)
Excel template for product management release readiness checklist template.
ریکارڈ Item-ID | چیک آئٹم | Category | حالت | severity | ذمہ دار | اردو ترجمہ: Reviewer | مقررہ تاریخ | جانچ کی تاریخ | Evidence | نوٹس
RDY-001 | All High or critical bugs fixed and QA pass | 1. Development & QA | مکمل | ضروری | Member 1 | Member 2 | 2026-06-10 | 2026-06-12 | https://example.com/qa/report | Regression testing completed on major browsers and mobile devices.
RDY-002 | Verify production monitoring and alerting configuration | 2. Infrastructure & Operations | ریکارڈ Verifying | ضروری | SRE Lead | ذمہ دار | 2026-06-14 |  | https://example.com/sre/monitoring | Final review of alert thresholds and notification channels in progress.
RDY-003 | Publish CS FAQ and primary response templates | 3. Sales & Customer Support | وقفہ شدہ | سفارش | ریکارڈ Support lead | ریکارڈ Product owner | 2026-06-15 |  | https://example.com/cs/faq | Waiting for final review of FAQ drafts.

## منظوری کی تاریخ (لاگ)
منظوری کی تاریخ (لاگ)
Excel template for product management release readiness checklist template.
منظوری کی آئی ڈی | ریکارڈ Department/role | منظور کرنے والے کا نام | فیصلہ نتیجہ | Approval Date | منظور کرنے والے کی رائے اور توثیق کے نکات
Sign-001 | پروڈکٹ ڈپارٹمنٹ | ریکارڈ Product owner | مشروط GO | 2026-06-16 | Release is approved on the condition of legal review completion.
Sign-002 | انجینئرنگ ڈپارٹمنٹ | ذمہ دار | GO | 2026-06-16 | QA report and major bug resolutions are confirmed.
Sign-003 | انفراسٹرکچر اور SRE ڈپارٹمنٹ | SRE Lead | GO | 2026-06-16 | Monitoring, backup, and rollback procedures are confirmed.

## معیارات کی ترتیبات (سیٹنگز)
معیارات کی ترتیبات (سیٹنگز)
Excel template for product management release readiness checklist template.
فیصلے کے زمرے | اجراء کے فیصلے کے ممبرز | ریکارڈ Department/role | Status Dictionary | Importance Master
1. Development & QA | Member 1 | پروڈکٹ ڈپارٹمنٹ | آئٹم | ضروری
2. Infrastructure & Operations | Member 2 | انجینئرنگ ڈپارٹمنٹ | ریکارڈ Verifying | سفارش
3. Sales & Customer Support | ریکارڈ Product owner | انفراسٹرکچر اور SRE ڈپارٹمنٹ | مکمل | ریکارڈ Optional