## Guide
Project Risk Register and Tracking Template
A free Excel template for registering, scoring, tracking, and reviewing project risks. It includes guide, dashboard, project settings, risk register, response actions, issue escalation, review log, and scenario library sheets.
1. Align assumptions | Fill in company, project, scoring rules, statuses, and scenario lists on Project Settings. | Formulas calculate automatically
2. Register risks | Enter risks, issues, or opportunities in Risk Register and select scenario, category, likelihood, impact, owner, and response strategy.
3. Track actions | Split mitigation, transfer, acceptance, escalation, and other responses into executable actions with owners and due dates.
4. Escalate issues | When a risk becomes an issue, decision, or change request, record handling, meeting forum, and closure result in Issue Escalation.

## Dashboard
Dashboard
A free Excel template for registering, scoring, tracking, and reviewing project risks. It includes guide, dashboard, project settings, risk register, response actions, issue escalation, review log, and scenario library sheets.
Status | Count | Level | Column4 | Column5 | Column6 | Column7 | Column8
Identified |  | Very High |  | Not started |  | Open
Assessing |  | High |  | In progress |  | In progress
Responding |  | Medium |  | Pending confirmation |  | Pending confirmation

## Project Settings
Project Settings
A free Excel template for registering, scoring, tracking, and reviewing project risks. It includes guide, dashboard, project settings, risk register, response actions, issue escalation, review log, and scenario library sheets.
Risk status | Risk category | Business scenario | Response strategy | Record type | Escalation level | Action status | Priority | Issue status | Review status | Review cycle | Action type
Identified | Scope | Project Delivery | Avoid | Risk | Normal tracking | Not started | P1-Critical | Open | Planned | Daily | Prevent
Assessing | Schedule | Product Development | Reduce | Issue | Team lead | In progress | P2-High | In progress | In progress | Weekly | Mitigate
Responding | Cost | IT / Digital | Transfer | Opportunity | Project manager | Pending confirmation | P3-Medium | Pending confirmation | Completed | Biweekly | Contingency plan

## Risk Register
Risk Register
A free Excel template for registering, scoring, tracking, and reviewing project risks. It includes guide, dashboard, project settings, risk register, response actions, issue escalation, review log, and scenario library sheets.
Risk ID | Business Scenario | Department / Scope | Project / Process | Record Type | Risk Category | Risk Event | Root Cause | Impact | Trigger Signal | Identified Date | Risk Owner | Stakeholders | Likelihood | Impact Level | Inherent Score | Inherent Level | Response Strategy | Current Control | Residual Likelihood | Residual Impact | Residual Score | Status | Next Review | Review Frequency | Last Reviewed | Evidence / Link | Related Action | Escalation Level | Due Alert
R-001 | Project Delivery | PMO | North Port core upgrade | Risk | Scope | New customer reporting requirements expand the scope | New metrics were not confirmed before requirements freeze | May add development work and delay launch | New fields appeared in the requirements meeting | 2026-04-01 | Ming Li | PMO / Owner | 4 | 4 |  | High | Reduce | Weekly review and owner follow-up | 3 | 3 |  | Responding | 2026-05-01 | Weekly | 2026-04-20 | Evidence link | A-001 | Normal tracking
R-002 | Supply Chain / Procurement | Procurement | Critical equipment purchase | Risk | Supplier | Core component delivery is delayed | Supplier capacity is tight and overseas logistics slots are unstable | Affects production scheduling and customer delivery commitments | Supplier weekly report shows schedule slippage | 2026-04-03 | Fang Wang | PMO / Owner | 3 | 4 |  | High | Transfer | Weekly review and owner follow-up | 2 | 3 |  | Monitoring | 2026-05-02 | Weekly | 2026-04-21 | Evidence link | A-002 | Normal tracking
R-003 | Compliance / Legal | Legal Compliance | New region launch | Risk | Compliance | Privacy terms for the new market are not reviewed | Regulatory differences and approval path are unclear | May delay launch or trigger remediation | Contract review found policy gaps | 2026-04-05 | Mina Zhao | PMO / Owner | 3 | 5 |  | High | Avoid | Weekly review and owner follow-up | 2 | 4 |  | Assessing | 2026-05-03 | Weekly | 2026-04-22 | Evidence link | A-003 | Team lead

## Response Actions
Response Actions
A free Excel template for registering, scoring, tracking, and reviewing project risks. It includes guide, dashboard, project settings, risk register, response actions, issue escalation, review log, and scenario library sheets.
Action ID | Related Risk ID | Action Type | Action Description | Owner | Collaborators | Start Date | Due Date | Status | Progress | Priority | Deliverable / Evidence | Blocker | Last Updated | Days Until Due | Alert | Notes
A-001 | R-001 | Mitigate | Complete scope change impact assessment and prepare approval opinion | Ming Li | Product / Development | 2026-04-22 | 2026-05-03 | In progress | 55% | P2-High | Change assessment form |  | 2026-04-28
A-002 | R-001 | Communication / Training | Confirm freeze list and approval path for new requirements with the customer | Ming Li | Customer Success | 2026-04-24 | 2026-05-06 | Not started | 10% | P2-High | Meeting notes |  | 2026-04-28
A-003 | R-002 | Transfer / Insurance | Confirm quotation and lead time for backup suppliers | Fang Wang | Procurement | 2026-04-18 | 2026-05-01 | In progress | 70% | P2-High | Backup supplier quotation |  | 2026-04-28

## Issue Escalation
Issue Escalation
A free Excel template for registering, scoring, tracking, and reviewing project risks. It includes guide, dashboard, project settings, risk register, response actions, issue escalation, review log, and scenario library sheets.
Issue ID | Related Risk ID | Issue / Decision Type | Description | Impact | Owner | Raised Date | Target Resolution Date | Status | Escalation Level | Decision Needed | Meeting / Forum | Final Result | Closed Date | Days Remaining | Alert | Notes
I-001 | R-001 | Change request | Customer reporting definition needs scope decision for this release | If included, estimated effort increases by five workdays | Ming Li | 2026-04-23 | 2026-05-03 | In progress | Project manager | Approve the new requirement for this release? | Project weekly meeting | Pending confirmation
I-002 | R-007 | Customer escalation | Key customer is unhappy with delivery pace and needs recovery plan | Affects renewal negotiation and customer reputation | Yue Sun | 2026-04-26 | 2026-05-02 | Pending confirmation | Executive decision | Can recovery commitments and milestones be confirmed externally? | Customer escalation meeting | Recovery plan pending customer confirmation
I-003 | R-008 | Operational blocker | Order exception backlog and delayed exception-board interface | Creates SLA breach and complaint risk | Wei Zheng | 2026-04-24 | 2026-04-29 | In progress | Project manager | Assign temporary manual cleanup and prioritize interface fix? | Operations meeting | Temporary cleanup assigned

## Review Log
Review Log
A free Excel template for registering, scoring, tracking, and reviewing project risks. It includes guide, dashboard, project settings, risk register, response actions, issue escalation, review log, and scenario library sheets.
Review ID | Date | Meeting / Forum | Scope | Review Topic | New Risks | Closed Risks | Key Decision | Owner | Next Follow-up | Status | Notes
RV-001 | 2026-04-13 | Project weekly meeting | Project Delivery | Confirm unresolved items, risk owners, and due dates for the week | 2 | 0 | Move R-001 scope change into dedicated follow-up | Ming Li | 2026-04-20 | Completed
RV-002 | 2026-04-20 | Operations meeting | Operations Process | Review order exception SLA and build daily board | 1 | 0 | Escalate R-008 into issue I-003 | Wei Zheng | 2026-04-29 | In progress
RV-003 | 2026-04-28 | PMO risk review | Cross-functional | Focus on high risks, overdue actions, and customer escalations | 1 | 0 | Submit R-007 to customer escalation meeting decision | Yue Sun | 2026-05-02 | Planned

## Scenario Library
Scenario Library
A free Excel template for registering, scoring, tracking, and reviewing project risks. It includes guide, dashboard, project settings, risk register, response actions, issue escalation, review log, and scenario library sheets.
Scenario ID | Business Scenario | Process / Area | Risk Category | Example Risk Event | Common Trigger Signal | Typical Impact | Suggested Control / Response | Recommended Strategy | Suggested Review Frequency
S-001 | Project Delivery | Requirements Management | Scope | Critical requirements keep changing and cause scope creep | Frequent new requests and failed requirements freeze | Schedule delay, cost increase, and quality decline | Change review, impact assessment, and requirements freeze list | Reduce | Weekly
S-002 | Project Delivery | Schedule Management | Schedule | Key milestones depend on external approval | Approval path is unclear or signer is unavailable | Launch delay and idle resources | Approval matrix, early booking, and alternate signer | Reduce | Weekly
S-003 | Product Development | Technical Solution | Quality | Core functional design is not sufficiently validated | High POC failure rate and concentrated defects | Rework and failed customer acceptance | Architecture review, prototype validation, and test coverage threshold | Reduce | Biweekly