## Instructions
Project Management Retrospective Report Spreadsheet Template
Use this template to review software projects, marketing campaigns, implementation work, operational improvements, and client delivery projects while capturing lessons and improvement actions.
Module | Purpose | Entry guidance
Metrics Dashboard | Summarizes key metrics, issue distribution, and action status | Usually for review only; avoid editing formula areas manually
Retrospective Overview | Records project background, scope, conclusions, and overall assessment | Enter project details first, then add the summary
Goals and Results | Compares planned goals with actual results | Set weight, completion rate, and variance reason for each core goal
Issues and Risks | Captures project issues, risks, impact, and root causes | Use it for retrospective discussion and prevention planning
Lessons Learned | Records what worked and what needs improvement | Write reusable principles rather than one-time impressions
Improvement Actions | Turns retrospective conclusions into owners, due dates, and status | Review open and overdue items every week
Meeting Notes | Records retrospective topics, participants, and decisions | Useful for cross-functional project archives
Reference Data | Provides dropdown options and classification lists | Adjust these terms to match internal wording
Workflow: 1) complete the overview; 2) enter goals and results; 3) organize issues, risks, and lessons; 4) create improvement actions; 5) review overall status on the metrics dashboard.

## Metrics Dashboard
Project Retrospective Metrics Dashboard
Summarizes goal achievement, issues, risks, lessons, and action status so managers can quickly judge review quality and follow-through.
Metric | Formula or Value | Notes | Action Status | Count | Impact Level | Count
Weighted Goal Achievement |  | Goal weight times completion rate | Not Started |  | High
High-impact Issues |  | Issues or risks with high impact | In Progress |  | Medium
Open Issues |  | Issues or risks not yet completed | Completed |  | Low
Total Improvement Actions |  | Number of action items | Delayed
Completed Actions |  | Status is completed
Action Completion Rate |  | Completed actions divided by total actions
Overdue Open Actions |  | Past due and not completed
Total Lessons |  | Entries in the lessons library

## Retrospective Overview
Project Management Retrospective Report - Overview
Centralize project basics, scope, goals, overall conclusions, and key review judgments.
Field | Content | Notes | Field | Content | Notes
Project Name | Example: Corporate Website Redesign | Required | Project Type | Software Development | Can be changed to marketing, implementation, or operations
Project Owner | John Miller | Required | Review Date | 2026-04-29 | Retrospective meeting date
Start Date | 46037 | Planned or actual start | End Date | 46132 | Actual end or phase end
Budget | 300000 | Project budget | Actual Cost | 328000 | Final cost
Planned Duration (days) |  | Calculated automatically | Actual Duration (days) |  | Adjust based on actual dates
Overall Assessment | Mostly achieved, with cost and scope-change pressure | Short conclusion | Project Phase | Completed | Initiation, execution, acceptance, completion
Review Facilitator | Emily Carter |  | Participating Teams | Product, Engineering, Marketing, Customer Support
Review Scope | Requirements, plan, delivery, quality, communication, risk, customer acceptance |  | Out of Scope | Commercial negotiation outside the contract
Key Conclusion | Core goals were mostly achieved; schedule remained controlled, but cost was high and the scope-freeze process needs improvement. |  | Next Focus | Create a change review process and strengthen milestone acceptance.

## Goals and Results
Goals and Results Comparison
Track planned goals, actual results, completion rate, variance, and lessons in one table to review whether the project achieved its business goals.
Goal ID | Goal or Result | Category | Weight | Plan | Actual | Unit | Completion Rate | Variance Notes | Owner | Review Conclusion
GOAL-001 | Release core feature modules | Scope | 30% | 12 | 11 | items |  | One low-priority feature was delayed | Product Manager | Priority tiers worked well
GOAL-002 | Complete customer acceptance on time | Schedule | 25% | 1 | 1 | yes/no |  | Accepted on schedule | Project Manager | Early acceptance checklist confirmation worked well
GOAL-003 | Control project cost | Cost | 20% | 300000 | 328000 | USD |  | Scope changes increased vendor cost | Finance and Project Management | Change review should happen earlier
GOAL-004 | Defect closure rate | Quality | 15% | 95% | 91% | % |  | Testing window was too short | Quality Lead | Keep buffer for regression testing
GOAL-005 | Key stakeholder satisfaction | Customer and Collaboration | 10% | 4.5 | 4.2 | score |  | Communication frequency was insufficient | Customer Success | A fixed weekly reporting rhythm worked well

## Issues and Risks
Issue and Risk Register
Record project issues, risks, root causes, impact, and prevention measures for cross-industry retrospectives.
ID | Type | Title | Phase | Impact | Probability | Impact Description | Root Cause | Response or Prevention | Owner | Status | Due Date
ISSUE-001 | Scope Change | Customer added an urgent reporting request | Execution | High | Medium | Added engineering and testing effort | Scope freeze point was unclear | Create a change request and impact assessment | Project Manager | In Progress | 2026-05-10
ISSUE-002 | Schedule Delay | Integration testing started later than planned | Execution | Medium | Medium | Reduced testing time | External dependency was not locked early | Add key dependencies to milestone readiness checks | Technical Lead | Completed | 2026-04-18
ISSUE-003 | Communication | Business acceptance criteria were inconsistent | Acceptance | Medium | Low | Increased rework and coordination effort | Acceptance examples were insufficient | Confirm acceptance cases during requirements | Product Manager | In Progress | 2026-05-15
ISSUE-004 | Quality Defect | Permission vulnerability found before release | Testing | High | Low | Created release security risk | Permission matrix was not reviewed separately | Add permission review checklist and security testing | Quality Lead | Completed | 2026-04-12
ISSUE-005 | Resource Shortage | Designer was reassigned temporarily | Execution | Medium | Medium | Interface review was delayed | Resource conflicts had no early warning | Include key resources in weekly capacity review | Department Manager | Not Started | 2026-05-20

## Lessons Learned
Lessons Learned Library
Convert retrospective conclusions into reusable lessons for future initiation, planning, execution, acceptance, and operations.
ID | Category | Topic | Use Case | Evidence | Lesson | Recommended Practice | Reusability | Responsible Team | Add to Standard Process
LESSON-001 | Worked Well | Milestone acceptance checklist | Customer delivery and software projects | Acceptance passed on the first attempt | Confirming acceptance examples early reduced disputes | Define the acceptance checklist during requirements review | High | Project Management Office | Yes
LESSON-002 | Needs Improvement | Scope-freeze process | Cross-functional projects | Multiple scope changes | Cost and schedule impact assessment was missing | Create change review and customer confirmation flow | High | Product and Project Management Office | Yes
LESSON-003 | Worked Well | Visual weekly report | Projects with many stakeholders | Customer satisfaction was high | A transparent weekly rhythm reduced misunderstanding | Publish weekly risk, progress, and decision lists | Medium | Project Manager | Yes
LESSON-004 | Needs Improvement | Insufficient test buffer | Release projects | Regression testing time was compressed | The plan did not reserve enough defect-fix buffer | Keep testing buffer on the critical path | High | Quality and Engineering | Yes
LESSON-005 | Hypothesis to Validate | Early vendor lock-in window | Projects with external dependencies | Integration testing was delayed | External resource availability affects the critical path | Include procurement and vendors in milestone planning | Medium | Procurement and Technology | No

## Improvement Actions
Improvement Action Plan
Turn retrospective findings into specific actions and track owners, priority, status, due dates, and verification method.
Action ID | Source ID | Action Category | Improvement Item | Specific Action | Owner | Priority | Status | Start Date | Due Date | Verification or Completion Standard
ACTION-001 | ISSUE-001 | Process Improvement | Create a scope-change review process | Add a change request form and confirm cost, schedule, and risk before approval | Project Manager | High | In Progress | 2026-04-30 | 2026-05-10 | Every new requirement has a review record
ACTION-002 | LESSON-004 | Quality Control | Reserve regression testing buffer | Add at least 10% test buffer to the project plan template | Quality Lead | High | Not Started | 2026-05-01 | 2026-05-20 | New project plans include a test-buffer line
ACTION-003 | ISSUE-003 | Customer Communication | Unify acceptance criteria | Create an acceptance example library and sign-off during requirements | Product Manager | Medium | In Progress | 2026-04-30 | 2026-05-15 | Acceptance cases map one-to-one with requirements
ACTION-004 | LESSON-003 | Knowledge Capture | Standardize project weekly reports | Design a weekly report template for progress, risks, decisions, and next-week plan | Project Management Office | Medium | Completed | 2026-04-25 | 2026-05-05 | Template is published and used by new projects
ACTION-005 | ISSUE-005 | Resource Allocation | Create key resource capacity review | Check design, engineering, and testing resource conflicts every week | Department Manager | Medium | Not Started | 2026-05-03 | 2026-05-20 | Weekly meeting includes fixed resource-risk review

## Meeting Notes
Retrospective Meeting Notes
Record the meeting flow, key discussion, decisions, and follow-up tasks for project closure and organizational learning.
Meeting ID | Date | Meeting Topic | Facilitator | Participants or Teams | Agenda | Key Discussion | Decision | Follow-up Task | Note Taker
MEETING-001 | 2026-04-29 | Project retrospective meeting | Emily Carter | Product, Engineering, Quality, Customer Support | Goal achievement and variance | Cost variance mainly came from scope changes | Create a change review process | Project Management Office drafts the template | Michael Lee
MEETING-002 | 2026-05-06 | Improvement action review | Emily Carter | Project Management Office, Engineering, Quality | Action item progress | Test buffer template should become part of planning standards | Update the plan template | Quality team provides standard fields | Michael Lee

## Reference Data
Reference Data / Dropdown Options
Status | Priority | Impact Level | Project Type | Issue Type | Review Category | Action Category
Not Started | High | High | Software Development | Scope Change | Worked Well | Process Improvement
In Progress | Medium | Medium | Marketing Campaign | Schedule Delay | Needs Improvement | Tool Improvement
Completed | Low | Low | Implementation | Cost Overrun | Hypothesis to Validate | Training
Delayed |  |  | Operational Improvement | Quality Defect | Reusable Practice | Risk Prevention
Canceled |  |  | Client Delivery | Communication |  | Customer Communication
|  |  | Internal Management | Resource Shortage |  | Quality Control
|  |  | Research and Development | Vendor Issue |  | Resource Allocation
|  |  |  | Customer Request |  | Knowledge Capture
Technical Risk
Process Issue