## Guide
Milestone Tracker Template
A free Excel template for organizing project milestones. It includes guide, settings, task register, monthly milestones, weekly coordination, meetings and deliverables, dashboard, and configuration dictionary sheets.
Step | Worksheet | What to do | Output / checkpoint
1 | Settings | Enter the project, client or company, owner, base date, update cadence, and governance roles. | Standardize the date basis and generate the current week and current month.
2 | Task Register | Maintain planned and actual dates, status, owner, and risk for issues, risks, actions, tasks, and milestones. | Automatically calculate planned days, actual days, variance days, and health.
3 | Monthly Milestones | Review monthly planned periods and actual completion points for project meetings, monthly reports, and portfolio reviews. | Review the planned and actual rhythm for the next six months.

## Settings
Settings
A free Excel template for organizing project milestones. It includes guide, settings, task register, monthly milestones, weekly coordination, meetings and deliverables, dashboard, and configuration dictionary sheets.
Role / team | Name / team | responsibilities | Notification method | Notes
Project manager | PMO | Overall plan, milestones, risks, and pre-meeting materials. | Weekly meeting / email | Template owner
Business owner | Business team | Requirement sign-off, acceptance criteria, and business priority. | Weekly meeting / chat
Delivery team | Project team | Run tasks, update actual progress, and submit blockers. | Daily standup / weekly meeting

## Task Register
Task Register
A free Excel template for organizing project milestones. It includes guide, settings, task register, monthly milestones, weekly coordination, meetings and deliverables, dashboard, and configuration dictionary sheets.
No | Project / workstream | Business scenario | Category | Phase | Milestone / task name | Owner | Partner / client | Priority | Status | Milestone level | Planned start | Planned finish | Actual start | Actual finish | Completion | Planned days | Actual days | Variance days | Health | Risk level | Blocked items | This week focus | Next action | Notes | Source / link
No | Digital upgrade | Software / digital | Milestone | Requirements / scope | Requirements sign-off | John Carter | Business team / client | High | Completed | L1 phase | 2026-04-20 | 2026-04-22 | 2026-04-20 | 2026-04-22 | 100% | 3 | 3 | 0 | Health | Low | No | No | Archive review notes | Scope confirmed
No | Digital upgrade | Software / digital | Risk | Requirements / scope | Scope change tracking | Emily Davis | Business team | High | In progress | L2 key task | 2026-04-23 | 2026-04-30 | 2026-04-23 |  | 55% | 8 | 9 | 1 | Health | High | No | Yes | Confirm change impact and approval path | Management needs to confirm scope boundaries
No | Procurement initiative | Procurement supply chain | Action | Procurement / delivery | Supplier follow-up | Michael Brown | Supplier Alpha | Medium | Pending | L2 key task | 2026-04-28 | 2026-05-05 |  |  | 30% | 8 |  | 0 | Health | Medium | No | Yes | Collect quotation and lead-time commitment | Waiting for supplier confirmation

## Monthly Milestones
Monthly Milestones
A free Excel template for organizing project milestones. It includes guide, settings, task register, monthly milestones, weekly coordination, meetings and deliverables, dashboard, and configuration dictionary sheets.
Plan | Actual | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12
Plan
Plan
Plan

## Weekly Coordination
Weekly Coordination
A free Excel template for organizing project milestones. It includes guide, settings, task register, monthly milestones, weekly coordination, meetings and deliverables, dashboard, and configuration dictionary sheets.
Date | Day | Daily focus | Planned items | Owner / team | Key meeting / deliverable | Risk / blocker | Notes
2026-04-27 | Monday | Weekly plan check | 4 |  |  |  | Confirm open items first
2026-04-28 | Tuesday | Risk review | 5 |  |  |  | Sync owners and due dates
2026-04-29 | Wednesday | ActionFollow-up | 6 |  |  |  | Confirm pending approvals

## Meetings and Deliverables
Meetings and Deliverables
A free Excel template for organizing project milestones. It includes guide, settings, task register, monthly milestones, weekly coordination, meetings and deliverables, dashboard, and configuration dictionary sheets.
No | Type | Subject | Date and time | Owner | Participants / location | Related milestone | Status | Minutes / deliverable | Follow-up action | Impacted milestone | Notes | Month | Event count | Completed | Incomplete / pending confirmation
No | Meeting | Project coordination meeting | 2026-05-01 08:30 | PMO | Project team / online meeting | Month-end close | Completed | Sync this week plan and risks | Follow up overdue items | Yes |  | Month | 9 | Completed | Incomplete Pending Confirmation
No | Review | Requirements sign-off review | 2026-05-04 10:00 | Business owner | Client / project team / meeting room | Requirements sign-off | Planned | Requirement approval pack | Confirm approver | Yes |  | Month | 1 | Completed | Incomplete Pending Confirmation
No | Follow-up | Supplier follow-up meeting | 2026-05-05 13:00 | Procurement owner | Supplier Alpha / procurement team | Supplier follow-up | Planned | Complete quotation and lead time | Update register status | Yes |  | Month | 0 | Completed | Incomplete Pending Confirmation

## Dashboard
Dashboard
A free Excel template for organizing project milestones. It includes guide, settings, task register, monthly milestones, weekly coordination, meetings and deliverables, dashboard, and configuration dictionary sheets.
Status | Count | Health | Column4 | Business scenario | Item count
Not started | 3 | On track | 5 | Software / digital | 4
Planned | 1 | Needs attention | 7 | Product launch | 1
In progress | 6 | Overdue | 1 | Engineering / construction | 1

## Configuration Dictionary
Configuration Dictionary
A free Excel template for organizing project milestones. It includes guide, settings, task register, monthly milestones, weekly coordination, meetings and deliverables, dashboard, and configuration dictionary sheets.
Status | Category | Priority | Risk level | Business scenario | Phase | Milestone level | Event type
Not started | Task | High | High | Software / digital | start | L0 strategy | Meeting
Planned | Milestone | Medium | Medium | Product launch | Requirements / scope | L1 phase | Review
In progress | Issue | Low | Low | Engineering / construction | Design / solution | L2 key task | Deliverable