## 01_Instructions
Project Charter Template ¦ General Edition
Light yellow cells are input areas; light blue cells are automatic calculation areas; cells with dropdown arrows can be selected directly. Suitable for IT, product, marketing, operations, compliance, engineering, customer delivery, and other business scenarios.
Charter completion |  | Current project | Average milestone completion |  |  | High and critical risk count
How to use this template |  |  |  | Milestone status overview
1 | Fill in basic information, business rationale, scope boundaries, and governance authorization in 02_Project Charter. |  |  | Status | Count
2 | Select the business scenario in 03_Scenario Settings, then review suggested deliverables, risks, and success metrics. |  |  | Not started
3 | Use 04_Goals Scope to break the vision into measurable goals, deliverables, assumptions, constraints, and dependencies. |  |  | In progress
4 | Maintain the high-level plan in 05_Milestones; duration, delay, and average completion rate are calculated automatically. |  |  | Blocked
5 | Add governance details in 06_Stakeholders RACI, 07_Risks Issues Changes, and 08_Budget Resources. |  |  | Completed
6 | Submit 09_Approval Log to complete authorization, and revisit the charter regularly during the project lifecycle. |  |  | Canceled
Sheet navigation
Sheet | Purpose
02_Project Charter | A one-page authorization document for quick review by the sponsor, PMO, and business owner.
03_Scenario Settings | Lists typical deliverables, focus areas, common risks, and success metrics by business scenario.
04_Goals Scope | Turns the vision into measurable goals, scope boundaries, and acceptance criteria.
05_Milestones | Records high-level phases, milestones, planned and actual dates, completion rates, and dependencies.
06_Stakeholders RACI | Identifies stakeholders, influence, communication frequency, and RACI responsibilities.
07_Risks Issues Changes | Centralizes risks, issues, and change requests with scoring and status tracking.
08_Budget Resources | Estimates costs and tracks actual spending and key resource inputs.
09_Approval Log | Keeps kickoff approvals, key decisions, and later sign-off records.
10_Data Dictionary | Maintains dropdown options and reference sources.

## 02_Project Charter
Project Charter
Clarifies why the project exists, its authorized scope, success criteria, governance mechanism, and approval requirements during kickoff.
Template completion
1. Project basics
Project name | Customer portal refresh project |  | Project ID | PC-2026-001 |  | Version | v1.0 | Created date | 2026-04-29
Company / business unit | East Region Business Unit |  | Department | Customer Success |  | Business scenario | IT / system launch | Project type | Operations improvement
Project sponsor | Olivia Chen |  | Project manager | Daniel Park |  | Project level | Department level | Charter status | Pending approval
Planned start | 2026-05-01 |  | Planned finish | 2026-07-15 |  | Total budget | 180000 | Currency | USD
2. Background, purpose, and business rationale
Business problem / opportunity |  | The current customer portal only accepts forms, so customers cannot check progress by themselves and support agents repeat the same status updates.
Project purpose / business rationale |  | Refresh the portal within one quarter so customers can submit requests, check status, and receive notifications without manual follow-up.
Strategic alignment / expected benefit |  | Supports the customer success goal of improving renewal experience and the operations goal of reducing repeated handling.
Impact of not doing the project |  | If the project does not start, status inquiries are expected to keep growing next quarter, putting response time and satisfaction at risk.
3. Goals, scope, and delivery
High-level goal |  | Launch customer self-service submission, status tracking, notification subscription, and basic support admin settings.
In scope |  | Customer portal screens, support intake dashboard, notification templates, permissions, and user training.
Out of scope |  | CRM master data redesign, native mobile apps, third-party payments, and deep cleanup of historical data are excluded.
Key deliverables |  | Requirements sign-off, prototype, test report, launch plan, training materials, and operations handover checklist.
Acceptance / success criteria |  | 95% UAT pass rate, 60% self-service intake in the first month, and all P1/P2 defects closed.
Key assumptions
Constraints and dependencies
4. Governance, authorization, and approval
Decision mechanism | Weekly meetings handle normal items; scope, budget, or launch date changes go to the project committee. |  |  |  | Reporting cadence | Share progress, risks, and decisions needed with the sponsor every Friday.
Escalation path |  |  |  |  | Project manager authority
Kickoff approver | Olivia Chen |  |  |  | Approval date | 2026-04-30 |  | Approval status | Pending approval
Approval notes
Note: this sheet is the project authorization summary. Maintain detailed goals, scope, plans, budgets, risks, stakeholders, and approval records in the following sheets.

## 03_Scenario Settings
Business scenario settings
Select a business scenario based on the company and project type to quickly identify deliverables, risks, and success metrics to watch.
Current charter scenario
Suggested focus
Scenario library
Business scenario | Applicable company / project | Core focus | Common deliverables | Common risks | Suggested success metrics
IT / system launch | System implementation, SaaS launch, platform migration, automation project | Requirement clarity, data migration, permissions, security, launch window, operations handover | Requirement confirmation, architecture plan, test report, launch plan, training materials, operations manual | Requirement changes, integration failure, poor data quality, insufficient downtime window, low user adoption | On-time launch rate, defect closure rate, user adoption rate, system availability, budget variance
Product development / new product | Software, hardware, or service product development and commercialization | Market assumptions, MVP scope, technical feasibility, quality gates, launch cadence | Product requirements, prototype or MVP, test validation, launch materials, commercialization plan | Requirement creep, technical infeasibility, insufficient testing, launch delay, margin shortfall | MVP delivery date, quality defect rate, pilot conversion rate, revenue or margin target
Marketing campaign | Brand promotion, acquisition campaign, channel event, content project | Target audience, budget return, channel mix, creative approval, data attribution | Campaign plan, budget sheet, content assets, channel plan, retrospective report | Insufficient reach, low conversion, compliance risk, supplier delay, budget overrun | Lead count, conversion rate, CAC, ROI, brand reach
Operations process improvement | Cost reduction, efficiency improvement, process redesign, service quality improvement | Current baseline, process boundaries, role responsibilities, change management, ongoing monitoring | Process map, SOP, training plan, pilot report, KPI dashboard | Frontline resistance, inconsistent data definitions, hard-to-verify benefits, cross-department dependencies | Cycle-time reduction, cost savings, error-rate reduction, SLA attainment
Compliance / audit remediation | Regulatory remediation, internal control buildout, information security, quality system | Regulatory clauses, evidence retention, owner, due date, audit trail | Remediation plan, control matrix, evidence package, training records, audit report | Insufficient evidence, unclear ownership, remediation delay, regulatory interpretation variance | On-time remediation rate, audit pass rate, defect recurrence rate, evidence completeness
Engineering / facility build | Factory, store, laboratory, office space, equipment installation | Safety, permits, suppliers, site conditions, acceptance criteria, budget control | Design plan, construction plan, acceptance checklist, safety records, handover documents | Permit delay, site change, safety incident, material price increase, quality rework | Completion date, first-pass acceptance rate, safety incident count, budget variance
Customer delivery / service implementation | B2B customer project, consulting delivery, customized service | Customer scope confirmation, contract boundaries, acceptance mechanism, communication cadence, change control | SOW, project plan, deliverable list, acceptance report, customer training | Customer requirement changes, unclear acceptance criteria, resource conflicts, low satisfaction | On-time delivery rate, customer satisfaction, change revenue or cost, acceptance pass rate
Data / BI project | Data warehouse, dashboard, analytics model, AI application pilot | Data sources, metric definitions, permissions, model accuracy, business adoption | Data dictionary, metric definitions, dashboard, model validation report, user guide | Poor data quality, definition disputes, limited permissions, model misuse, low adoption | Data accuracy, report usage rate, processing timeliness, model accuracy
Supply chain / procurement project | Supplier switch, procurement savings, inventory optimization, logistics improvement | Supply risk, contract terms, quality validation, inventory impact, delivery continuity | Supplier evaluation, negotiation plan, contract, transition plan, quality validation report | Supply interruption, unstable quality, price volatility, contract risk, inventory buildup | Procurement savings, on-time delivery rate, quality pass rate, inventory turnover
Organizational change / M&A integration | Organizational adjustment, M&A integration, shared services, cultural change | Leadership alignment, communication plan, people impact, system and process integration, change adoption | Change roadmap, communication package, organization design, training plan, integration report | Employee resistance, key talent loss, cultural conflict, uncontrolled pace | Adoption rate, employee retention rate, synergy benefits, key milestone completion rate
Other | Unclassified or hybrid project | Clarify goals, scope boundaries, resource constraints, risk assumptions, and approval mechanism | Charter, plan, budget, risk list, approval records | Unclear goals, scope creep, insufficient resources, delayed decisions | Goal achievement rate, schedule variance, budget variance, stakeholder satisfaction

## 04_Goals Scope
Goals, scope, and deliverables
Break the charter vision into measurable goals, scope boundaries, deliverables, assumptions, constraints, and dependencies.
1. Measurable goals and success criteria
No. | Goal category | Goal description | Metric / KPI | Baseline | Target value | Verification method | Owner | Due date | Status | Notes
1 | Efficiency | Unify customer self-service submission and progress tracking in the new portal | Self-service intake rate | Current 35% | 60% after launch | Monthly support report | Daniel Park | 2026-07-15 | In progress | Align with support system tracking
2
3
4
5
6
7
8
9
10
2. Scope boundaries, deliverables, and acceptance
Type | Item | Description | Acceptance / measurement method | Owner | Target date | Priority | Status | Notes
In scope | Customer self-service submission | Portal form, attachment upload, status tracking, and notification subscription | All UAT cases pass | Daniel Park | 2026-06-20 | High | In progress | Core scope
Out of scope
Key deliverables
Acceptance criteria
Key assumptions
Constraints
Key dependencies
Exclusions

## 05_Milestones
Milestone Plan
Used for high-level kickoff planning, not as a replacement for a detailed Gantt chart; it focuses on phases, milestones, dates, dependencies, and variances needed for authorization.
Total milestones |  |  |  | Completed |  |  |  | Overdue / delayed
High-level milestones
Phase | Milestone / key task | Primary deliverable | Owner | Planned start | Planned finish | Actual finish | Planned duration | Delay days | Completion rate | Status | Dependencies / notes
Initiation | Project charter approved | Approved charter | Olivia Chen | 2026-05-01 | 2026-05-03 | 2026-05-03 |  |  | 100% | Completed | Project formally authorized
Formulas:
Delay days = IF([Planned finish]="","",IF([Actual finish]<>"",[Actual finish]-[Planned finish],IF(AND(TODAY()>[Planned finish],[Status]<>"Completed",[Status]<>"Canceled"),TODAY()-[Planned finish],0)))

## 06_Stakeholders RACI
Stakeholders and RACI
Identifies key stakeholders and clarifies responsibilities to avoid vague authority, communication gaps, or approval delays after kickoff.
1. Stakeholder list
ID | Stakeholder / team | Organization / role | Power | Interest | Influence | Needs / expectations | Communication frequency | Relationship owner | Contact information | Management strategy
S01 | Customer success lead | Business sponsor | High | High | High | Improve customer experience and reduce repeated inquiries | Weekly | Daniel Park | olivia@example.com | Keep one-page progress and risk updates
S02
S03
S04
S05
S06
S07
S08
S09
S10
S11
S12
S13
S14
S15
2. RACI Responsibility Matrix (R=Responsible, A=Accountable, C=Consulted, I=Informed)
Deliverable / decision | Project sponsor | Project manager | Business owner | Technical / product owner | Finance | Legal / compliance | Procurement / supplier | Operations / customer support | PMO | Other 1 | Other 2 | Notes
Charter approval | A | R | C | C | C | C | I | I | C

## 07_Risks Issues Changes
Risks, issues, and changes
Identifies high-level risks during kickoff and manages issues and changes during execution to keep governance closed across scope, cost, schedule, and quality.
1. Risk register
ID | Category | Risk description | Probability 1-5 | Impact 1-5 | Score | Level | Response strategy | Owner | Due date | Status | Mitigation / contingency
R01 | Scope | Customer inquiry scope keeps expanding and threatens launch date | 3 | 4 |  |  | Mitigate | Olivia Chen | 2026-05-10 | In handling | Set change threshold and include only open records from the last 90 days
R02
R03
R04
R05
R06
R07
R08
R09
R10
R11
R12
R13
R14
R15
R16
R17
R18
R19
R20
2. Issue list
ID | Issue description | Influence | Priority | Owner | Raised date | Target resolution date | Status | Decision / action | Linked risk | Closed date | Notes
I01 | Notification SMS template needs opt-out wording | Launch copy requires rework | High | Sophia Kim | 2026-05-06 | 2026-05-12 | In handling | Add standard opt-out wording and complete compliance review | R02
I02
I03
I04
I05
I06
I07
I08
I09
I10
I11
3. Change request
ID | Change type | Change description | Reason | Impact area | Cost impact | Schedule impact | Requester | Request date | Approval status | Approver | Notes
C01 | Scope adjustment | Add email channel to notification subscription | Customers want email alerts as well | Frontend, notification templates, test cases | 12000 | Add 3 days | Mia Wong | 2026-05-09 | Under assessment | Olivia Chen | Confirm budget buffer
C02
C03
C04
C05
C06
C07
C08
C09
C10
C11

## 08_Budget Resources
Budget and Resources
Records high-level kickoff budget, actual spending, and key resource needs as the basis for approval and later cost control.
Estimated total |  |  |  | Approved total |  |  |  | Budget variance
1. Budget detail
Cost category | Item / description | Estimated amount | Approved amount | Actual amount | Variance | Capitalized | Owner | Procurement / contract status | Notes
Labor | Internal project management and business acceptance | 32000 | 32000 | 0 |  | No | Olivia Chen | Confirmed | Internal effort estimate
2. Key resource needs
Resource type | Resource name / team | Role / purpose | Allocation % | Start date | End date | Rate / hour | Estimated hours | Estimated cost | Status / notes
People | Customer success representative | UAT and process confirmation | 30% | 2026-05-04 | 2026-07-15 | 220 | 120 |  | Scheduled

## 09_Approval Log
Approval Records and Decision Log
Keeps project kickoff authorization, key deliverable approvals, decisions, and later change approvals.
1. Kickoff and phase approvals
No. | Approval item / deliverable | Approver | Role | Due approval date | Actual approval date | Approval result | Sign-off / confirmation method | Comments | Notes
1 | Project charter | Olivia Chen | Project sponsor | 2026-04-30 | 2026-04-30 | Approved | Email confirmation | Approved to start with current scope
2
3
4
5
6
7
8
9
10
11
12
13
14
15
2. Key decision log
ID | Decision topic | Background / issue | Decision content | Decision maker / committee | Decision date | Impact area | Follow-up action | Owner | Status
D01 | Deliver responsive web first | Native app investment is too large for this phase | Do not build a native app; keep responsive web adaptation | Project committee | 2026-04-30 | Scope, budget | List as out of scope | Olivia Chen | Completed
D02
D03
D04
D05
D06
D07
D08
D09
D10
D11
D12
D13
D14
D15
D16
Authorization statement: after approval, the project manager may organize resources and move the project forward within the scope, budget, and governance boundaries defined in this charter; items beyond scope, budget, or key constraints must be approved through the change process.

## 10_Data Dictionary
Data Dictionary and References
This sheet maintains template dropdown options and lists reference sources for the project charter structure; adjust it to match company governance rules.
Business scenario | Project type | Project level | Charter status | Milestone status | Priority | Risk response | Approval result
IT / system launch | Strategic project | Company level | Draft | Not started | High | Avoid | Pending approval
Product development / new product | Operations improvement | Department level | Pending approval | In progress | Medium | Mitigate | Approved
Marketing campaign | Product / service | Team level | Approved | Blocked | Low | Transfer | Conditionally approved
Operations process improvement | IT / data | Pilot | Returned for revision | Completed |  | Accept | Returned for revision
Compliance / audit remediation | Compliance / risk control |  | Paused | Canceled |  | Exploit | Rejected
Engineering / facility build | Customer delivery |  | Canceled |  |  | Share
Customer delivery / service implementation | Engineering / facility |  | Archived
Data / BI project | Organizational change
Supply chain / procurement project | Other
Organizational change / M&A integration
Other
Other dropdown options
Power/Interest/Influence | Probability/impact score | Issue status | Change status | Cost category | Resource type | RACI | Communication frequency
High | 1 | New | Submitted | Labor | People | R | Daily
Medium | 2 | In handling | Under assessment | Materials / procurement | Equipment | A | Weekly
Low | 3 | Decision pending | Approved | Software / cloud service | Software | C | Biweekly
| 4 | Resolved | Rejected | Outsourcing / consulting | Data | I | Monthly
| 5 | Closed | Implemented | Equipment / assets | Vendors | - | By milestone
|  |  | Closed | Travel | Site |  | As needed
|  |  |  | Training | Funding
|  |  |  | Compliance / certification | Other
Contingency
Other
Reference sources used to derive common project charter fields
Source | URL | Referenced template elements
ProjectManager: Project Charter Template for Excel | https://www.projectmanager.com/templates/project-charter-template-excel | Project purpose, authorization, goals, scope, stakeholders, budget, high-level plan, roles, success criteria, risks, milestones, resources, and approvals.
Atlassian / Confluence: Project Charter Template | https://www.atlassian.com/software/confluence/templates/project-charter | Project goals, scope, team members, stakeholders, resource needs, timeline, budget cost, risks, and strategic vision.
Excelx: Project Charter Template Excel | https://excelx.com/template/project-charter/ | Project overview, time and budget, scope, goals, stakeholders, risk mitigation, roles and responsibilities, milestones, and approval tracking.
CNY | Scope change | Yes | Not started | Pending confirmation | Not executed | In scope
USD | Budget change | No | Quoting | Confirmed | In progress | Out of scope
EUR | Schedule change | TBD | In procurement | Gap identified | Completed | Deliverable
GBP | Quality or requirement change |  | Contracted | N/A | Retired | Acceptance criteria
JPY | Resource change |  | Paid |  |  | Key dependency
CAD | Contract change |  | N/A
AUD | Other
Other