## 01_Instructions
Project Charter Template ¦ General Edition
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
1 | Fill in basic information, business rationale, scope boundaries, and governance authorization in 02_Project Charter. | Status | Count
2 | Select the business scenario in 03_Scenario Settings, then review suggested deliverables, risks, and success metrics. | Not started
3 | Use 04_Goals Scope to break the vision into measurable goals, deliverables, assumptions, constraints, and dependencies. | In progress
4 | Maintain the high-level plan in 05_Milestones; duration, delay, and average completion rate are calculated automatically. | Blocked

## 02_Project Charter
02_Project Charter
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
Project name | Customer portal refresh project | Project ID | PC-2026-001 | Version | v1.0 | Created date | 2026-04-29
Company / business unit | East Region Business Unit | Department | Customer Success | Business scenario | IT / system launch | Project type | Operations improvement
Project sponsor | Olivia Chen | Project manager | Daniel Park | Project level | Department level | Charter status | Pending approval
Planned start | 2026-05-01 | Planned finish | 2026-07-15 | Total budget | 180,000 | Currency | USD

## 03_Scenario Settings
03_Scenario Settings
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
Business scenario | Applicable company / project | Core focus | Common deliverables | Common risks | Suggested success metrics
IT / system launch | System implementation, SaaS launch, platform migration, automation project | Requirement clarity, data migration, permissions, security, launch window, operations handover | Requirement confirmation, architecture plan, test report, launch plan, training materials, operations manual | Requirement changes, integration failure, poor data quality, insufficient downtime window, low user adoption | On-time launch rate, defect closure rate, user adoption rate, system availability, budget variance
Product development / new product | Software, hardware, or service product development and commercialization | Market assumptions, MVP scope, technical feasibility, quality gates, launch cadence | Product requirements, prototype or MVP, test validation, launch materials, commercialization plan | Requirement creep, technical infeasibility, insufficient testing, launch delay, margin shortfall | MVP delivery date, quality defect rate, pilot conversion rate, revenue or margin target
Marketing campaign | Brand promotion, acquisition campaign, channel event, content project | Target audience, budget return, channel mix, creative approval, data attribution | Campaign plan, budget sheet, content assets, channel plan, retrospective report | Insufficient reach, low conversion, compliance risk, supplier delay, budget overrun | Lead count, conversion rate, CAC, ROI, brand reach

## 04_Goals Scope
04_Goals Scope
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
No. | Goal category | Goal description | Metric / KPI | Baseline | Target value | Verification method | Owner | Due date | Status | Notes
1 | Efficiency | Unify customer self-service submission and progress tracking in the new portal | Self-service intake rate | Current 35% | 60% after launch | Monthly support report | Daniel Park | 2026-07-15 | In progress | Align with support system tracking
2
3

## 05_Milestones
05_Milestones
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
Phase | Milestone / key task | Primary deliverable | Owner | Planned start | Planned finish | Actual finish | Planned duration | Delay days | Completion rate | Status | Dependencies / notes
Initiation | Project charter approved | Approved charter | Olivia Chen | 2026-05-01 | 2026-05-03 | 2026-05-03 |  |  | 100% | Completed | Project formally authorized

## 06_Stakeholders RACI
06_Stakeholders RACI
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
Deliverable / decision | Project sponsor | Project manager | Business owner | Technical / product owner | Finance | Legal / compliance | Procurement / supplier | Operations / customer support | PMO | Other 1 | Other 2 | Notes
Charter approval | A | R | C | C | C | C | I | I | C

## 07_Risks Issues Changes
07_Risks Issues Changes
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
ID | Category | Risk description | Probability 1-5 | Impact 1-5 | Score | Level | Response strategy | Owner | Due date | Status | Mitigation / contingency
R01 | Scope | Customer inquiry scope keeps expanding and threatens launch date | 3 | 4 |  |  | Mitigate | Olivia Chen | 2026-05-10 | In handling | Set change threshold and include only open records from the last 90 days
R02
R03

## 08_Budget Resources
08_Budget Resources
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
Cost category | Item / description | Estimated amount | Approved amount | Actual amount | Variance | Capitalized | Owner | Procurement / contract status | Notes
Labor | Internal project management and business acceptance | 32,000 | 32,000 | 0 |  | No | Olivia Chen | Confirmed | Internal effort estimate
2. Key resource needs
Resource type | Resource name / team | Role / purpose | Allocation % | Start date | End date | Rate / hour | Estimated hours | Estimated cost | Status / notes

## 09_Approval Log
09_Approval Log
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
No. | Approval item / deliverable | Approver | Role | Due approval date | Actual approval date | Approval result | Sign-off / confirmation method | Comments | Notes
1 | Project charter | Olivia Chen | Project sponsor | 2026-04-30 | 2026-04-30 | Approved | Email confirmation | Approved to start with current scope
2
3

## 10_Data Dictionary
10_Data Dictionary
A free Excel template for project kickoff planning that organizes goals, scope, stakeholders, budget notes, and approvals in one workbook.
Business scenario | Project type | Project level | Charter status | Milestone status | Priority | Risk response | Approval result
IT / system launch | Strategic project | Company level | Draft | Not started | High | Avoid | Pending approval
Product development / new product | Operations improvement | Department level | Pending approval | In progress | Medium | Mitigate | Approved
Marketing campaign | Product / service | Team level | Approved | Blocked | Low | Transfer | Conditionally approved