## Instructions
Project Progress Visual Board Template
Designed for different companies and business contexts. It keeps project setup, tasks, milestones, risks, issues, weekly reports, and the management board together while asking for only the minimum required information.
Business Context | Typical Use | Fields to Watch | Board Focus
Software / IT | System launch, data migration, automation redesign | Stage, blockers, test and launch dates | Progress, risks, overdue tasks
Product Development | New product development, prototype validation, pilot production | Milestones, deliverables, quality risks | Stage completion rate, milestone completion rate
Marketing Campaign | Launch events, campaigns, content plans | Channels, budget, owner | Budget variance, task status

## Project Setup
Project Setup
Designed for different companies and business contexts. It keeps project setup, tasks, milestones, risks, issues, weekly reports, and the management board together while asking for only the minimum required information.
Project ID | Project Name | Business Context | Project Owner | Department or Client | Start Date | Planned Finish | Project Budget | Current Stage | Project Status | Update Rhythm | Next Review | Key Goal | Notes | Board Project Filter List
P-001 | CRM System Launch | Software / IT | Emily Carter | Sales Center | 2026-04-01 | 2026-06-30 | 280000 | Development / Execution | In Progress | Weekly | 2026-05-15 | Launch the sales process and create training materials. | Interface integration testing is on the critical path. | All Projects
P-002 | New Product Launch Campaign | Marketing Campaign | Olivia Parker | Marketing | 2026-04-15 | 2026-06-10 | 180000 | Design | Risk Alert | Weekly | 2026-05-13 | Complete launch release, channel content, and campaign preparation. | Budget approval needs follow-up.
P-003 | Warehouse Efficiency Improvement | Operations Improvement | Michael Brooks | Supply Chain | 2026-03-20 | 2026-07-15 | 120000 | Testing / Acceptance | In Progress | Biweekly | 2026-05-20 | Reduce picking errors and improve turnover efficiency. | On-site data validation is needed.

## Task Details
Task Details
Designed for different companies and business contexts. It keeps project setup, tasks, milestones, risks, issues, weekly reports, and the management board together while asking for only the minimum required information.
Task ID | Project Name | Business Context | Stage | Work Item / Task | Owner | Priority | Status | Start Date | Planned Finish | Actual Finish | Planned Hours | Actual Hours | Completion Rate | Planned Budget | Actual Cost | Overdue Days | Budget Variance | Health Status | Next Action | Notes
T-001 | CRM System Launch | Software / IT | Requirements | Confirm sales process fields and permissions | Emily Carter | P1-High | Completed | 2026-04-01 | 2026-04-12 | 2026-04-11 | 32 | 28 | 100% | 18000 | 16500 |  |  |  | Document the permission matrix
T-002 | CRM System Launch | Software / IT | Development / Execution | Develop the client master data sync interface | Technical Lead | P0-Urgent | In Progress | 2026-04-15 | 2026-05-09 |  | 80 | 72 | 70% | 52000 | 46000 |  |  |  | Complete the exception retry mechanism | Supplier interface documentation changed
T-003 | CRM System Launch | Software / IT | Testing / Acceptance | Organize key-user UAT | Technical Lead | P1-High | Not Started | 2026-05-18 | 2026-06-07 |  | 48 | 0 | 0% | 22000 | 0 |  |  |  | Prepare test cases

## Milestones
Milestones
Designed for different companies and business contexts. It keeps project setup, tasks, milestones, risks, issues, weekly reports, and the management board together while asking for only the minimum required information.
Milestone ID | Project Name | Milestones | Stage | Owner | Target Date | Completion Date | Status | Completion Rate | Overdue Days | Description | Deliverable | Next Action
M-001 | CRM System Launch | Requirements Freeze | Requirements | Emily Carter | 2026-04-12 | 2026-04-11 | Completed | 100% |  | Scope and permissions confirmed | Requirements Signoff
M-002 | CRM System Launch | UAT Start | Testing / Acceptance | Testing Lead | 2026-05-20 |  | Not Started | 0% |  | Waiting for interface development to finish | Test Plan | Complete test case preparation
M-003 | New Product Launch Campaign | Key Visual Confirmation | Design | Design Lead | 2026-05-12 |  | In Progress | 65% |  | Copy awaiting final confirmation | Final Key Visual | Leadership Confirmation

## Risks and Issues
Risks and Issues
Designed for different companies and business contexts. It keeps project setup, tasks, milestones, risks, issues, weekly reports, and the management board together while asking for only the minimum required information.
ID | Project Name | Type | Title | Description | Owner | Impact Level | Likelihood | Priority | Status | Logged Date | Target Resolution | Close Date | Risk Score | Overdue Days | Response / Solution | Latest Update | Escalation Flag
R-001 | CRM System Launch | Risk | Interface documentation changed | Supplier return fields changed and may affect integration testing. | Technical Lead | High | Medium | P0-Urgent | In Progress | 2026-05-02 | 2026-05-13 |  |  |  | Map the new fields and prepare a compatibility plan. | Latest draft received
R-002 | New Product Launch Campaign | Issue | Budget approval delayed | Campaign budget is not fully approved, affecting channel scheduling. | Marketing Lead | High | Occurred | P1-High | Open | 2026-05-05 | 2026-05-12 |  |  |  | Escalate to the marketing director for approval | Waiting for approval meeting
R-003 | Client Delivery Project A | Blocked | Client training delayed | The client key administrator is traveling, so training cannot finish on schedule. | Sarah Mitchell | Medium | Occurred | P1-High | In Progress | 2026-05-08 | 2026-05-14 |  |  |  | Provide a recording and make-up session options | Client confirmation in progress

## Weekly Reports
Weekly Reports
Designed for different companies and business contexts. It keeps project setup, tasks, milestones, risks, issues, weekly reports, and the management board together while asking for only the minimum required information.
Weekly Report ID | Project Name | Week Start | Week End | Reporter | This Week Progress | Key Items Completed | Next Week Plan | Risk / Issue Summary | Decision / Support Needed | Overall Status | This Week Completion Rate | Next Review | Meeting Link / Notes
W-001 | CRM System Launch | 2026-04-27 |  | Emily Carter | Interface development entered integration testing, and the permission matrix is complete. | Requirements frozen and permissions confirmed. | Complete retry logic and prepare UAT. | Supplier interface documentation changed. | Technical lead needs to confirm field mapping. | Watch | 62% | 2026-05-15 | Weekly meeting notes sent
W-002 | New Product Launch Campaign | 2026-04-27 |  | Olivia Parker | First key visual draft completed; channel schedule not frozen. | Campaign theme and asset list. | Complete budget approval and channel schedule. | Budget approval delayed. | Ask the marketing director to confirm campaign budget. | Risk | 48% | 2026-05-13
W-003 | Warehouse Efficiency Improvement | 2026-04-27 |  | Michael Brooks | Pilot started and first-week sampling completed. | Process sampling and first route draft. | Continue sampling and validate efficiency. | Risk of insufficient sample size. | Site supervisor support is needed. | On Track | 55% | 2026-05-20

## Visual Board
Visual Board
Designed for different companies and business contexts. It keeps project setup, tasks, milestones, risks, issues, weekly reports, and the management board together while asking for only the minimum required information.
Delayed / Watch Tasks | Project | Owner | Status | Planned Finish | Overdue Days | Next Action | Escalation Risks | Column9 | Column10 | Target Resolution | Column12 | Response Plan
Filter tip: In Task Details, filter Health Status to Delayed, Risk, or Watch and bring those items into the weekly meeting first. | [6 empty] | Filter tip: In Risks and Issues, filter Escalation Flag to Escalate.
Action tip: Copy key tasks into this area and record the owner, due date, and support needs. | [6 empty] | Escalation logic: High-score, P0, or overdue items are flagged for escalation automatically.
Expansion tip: Each company can further split tasks by department, client, or project portfolio. | [6 empty] | Meeting action: Confirm the response plan, owner, target resolution date, and support needs.