## Basic settings
Project Status Report Template
Project name | XX Apartment Building Project | Total tasks | 20
Project name | 1-2-3 XX, Tokyo | Not started | 14
Project lead | Zhang Wei | In progress | 2
Start date | 2026-04-01 | Done | 4
Planned end date | 2026-06-30 | Average progress | 26%
Progress rate check date | 2026-04-18
Base month for monthly plan (1st day) | 2026-04-01 | How to use 1. Enter the base dates and project name 2. Update the blue cells in the task master 3. Changes are reflected automatically in the monthly and weekly plans
Weekly status table start date (Monday) | 2026-04-13
Legend
Input cell | Cells for direct user input
Control cell | Settings such as base date and base month
Link/auto sync | Displayed by reference from the task master
Attention/delay | Items requiring delay tracking or review
This file is a template that combines a task master, monthly plan, weekly plan, and meeting/delivery progress into one workbook. You can overwrite the sample rows for your own use. Add rows as needed and copy the formulas downward.

## Status report master
Status report master
Project name | XX Apartment Building Project | [7 empty] | Total tasks | 20
[9 empty] | Not started | 14
[9 empty] | In progress | 2
No | Task category | Task name | Partner | Crew | Planned start | Planned end | Planned days | Actual start | Actual end | Actual days | Progress rate | Status | Delay days | Priority | Work location | Notes
1 | Planning | Kickoff prep | Project Alpha | 4 | 2026-04-01 | 2026-04-03 | 3 | 2026-04-01 | 2026-04-03 | 3 | 100% | Done | 0 | High | Project perimeter | Pre-start preparation
2 | Requirements | Setting out/excavation | Project Alpha | 6 | 2026-04-04 | 2026-04-08 | 5 | 2026-04-04 | 2026-04-08 | 5 | 100% | Done | 0 | High | Scope area | Includes soil disposal
3 | Design | Crushed stone base/lean concrete | Sato Civil Works | 5 | 2026-04-09 | 2026-04-10 | 2 | 2026-04-09 | 2026-04-10 | 2 | 100% | Done | 0 | High | Overall foundation
4 | Design | Rebar tying | Tanaka Rebar | 6 | 2026-04-11 | 2026-04-14 | 4 | 2026-04-11 | 2026-04-14 | 4 | 100% | Done | 0 | High | Overall foundation | Includes rebar inspection
5 | Design | Formwork | Takahashi Formwork | 5 | 2026-04-13 | 2026-04-16 | 4 | 2026-04-13 |  | 6 | 70% | In progress | 2 | High | Overall foundation | Partial rework
6 | Design | Design review | Central Ready-Mix | 8 | 2026-04-17 | 2026-04-18 | 2 | 2026-04-17 |  | 2 | 50% | In progress | 0 | High | Overall foundation | Weather confirmation needed
7 | Design | Strip forms/curing | Takahashi Formwork | 4 | 2026-04-19 | 2026-04-22 | 4 |  |  |  | 0% | Not started | 0 | Medium | Overall foundation
8 | Build | 1F structural work | Yamaguchi Project | 10 | 2026-04-23 | 2026-04-30 | 8 |  |  |  | 0% | Not started | 0 | High | 1F
9 | Testing | Roof waterproofing | Mizuno Testing | 4 | 2026-05-01 | 2026-05-04 | 4 |  |  |  | 0% | Not started | 0 | Medium | Roof
10 | Coordination | Window frame installation | Suzuki Windows | 4 | 2026-05-06 | 2026-05-10 | 5 |  |  |  | 0% | Not started | 0 | Medium | Exterior
11 | Integration | Electrical wiring (rough-in) | Toko Electrical | 5 | 2026-05-08 | 2026-05-16 | 9 |  |  |  | 0% | Not started | 0 | Medium | Each floor
12 | Support | Support (embedded piping) | Daiichi Equipment | 5 | 2026-05-08 | 2026-05-15 | 8 |  |  |  | 0% | Not started | 0 | Medium | Each floor
13 | Execution | Light-gauge framing base | Project Supports | 6 | 2026-05-17 | 2026-05-21 | 5 |  |  |  | 0% | Not started | 0 | Medium | Each floor
14 | Execution | Gypsum board installation | Project Supports | 7 | 2026-05-22 | 2026-05-27 | 6 |  |  |  | 0% | Not started | 0 | Medium | Each floor
15 | Execution | Painting | Central Painting | 4 | 2026-05-28 | 2026-05-31 | 4 |  |  |  | 0% | Not started | 0 | Medium | Each floor
16 | Launch prep | Fixture installation/trial run | Daiichi Equipment | 4 | 2026-06-01 | 2026-06-08 | 8 |  |  |  | 0% | Not started | 0 | High | Each floor
17 | Release prep | Release prep/paving | Sato Civil Works | 5 | 2026-06-09 | 2026-06-16 | 8 |  |  |  | 0% | Not started | 0 | Medium | Outdoor
18 | Review | Completion review | Supervisor/owner | 3 | 2026-06-20 | 2026-06-22 | 3 |  |  |  | 0% | Not started | 0 | High | Overall
19 | Fix | Rework | All subcontractors | 6 | 2026-06-23 | 2026-06-27 | 5 |  |  |  | 0% | Not started | 0 | High | Overall
20 | Done | Done | Prime contractor/owner | 2 | 2026-06-30 | 2026-06-30 | 1 |  |  |  | 0% | Not started | 0 | High | Office
Update the blue and purple cells. Status, days, and delay are calculated automatically. Copy the formulas below row 35 if you need to add more rows.

## Monthly status table
2026/04 Monthly status table
Project name | XX Apartment Building Project |  |  |  |  | Progress rate check date | 2026-04-18 |  |  |  | ■ | Planned | A | Actual
No | Task name | Partner | Status | Crew | Planned start | Planned end | Actual start | Actual end | Progress rate | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30
[10 empty] | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
1 | Kickoff prep | Project Alpha | Done | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | 100% | bar: 2026-04-01 to 2026-04-03
2 | Setting out/excavation | Project Alpha | Done | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 | 100% | bar: 2026-04-04 to 2026-04-08
3 | Crushed stone base/lean concrete | Sato Civil Works | Done | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 100% | bar: 2026-04-09 to 2026-04-10
4 | Rebar tying | Tanaka Rebar | Done | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 | 100% | bar: 2026-04-11 to 2026-04-14
5 | Formwork | Takahashi Formwork | In progress | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  | 70% | bar: 2026-04-13 to 2026-04-18
6 | Design review | Chuo Ready-Mix Concrete | In progress | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  | 50% | bar: 2026-04-17 to 2026-04-18
7 | Demolding/Curing | Takahashi Formwork | Not started | 4 | 2026-04-19 | 2026-04-22 |  |  | 0% | bar: 2026-04-19 to 2026-04-22
8 | 1F Structural Frame | Yamaguchi Project | Not started | 10 | 2026-04-23 | 2026-04-30 |  |  | 0% | bar: 2026-04-23 to 2026-04-30
9 | Roof Testing | Mizuno Testing | Not started | 4 | 2026-05-01 | 2026-05-04 |  |  | 0%
10 | Sash Installation | Suzuki Sash | Not started | 4 | 2026-05-06 | 2026-05-10 |  |  | 0%
11 | Electrical Wiring (Rough Wiring) | Toko Electrical | Not started | 5 | 2026-05-08 | 2026-05-16 |  |  | 0%
12 | Plumbing/Drainage Pre-piping | Daiichi Equipment | Not started | 5 | 2026-05-08 | 2026-05-15 |  |  | 0%
13 | Light Gauge Framing | Project Support | Not started | 6 | 2026-05-17 | 2026-05-21 |  |  | 0%
14 | PB Board Installation | Project Support | Not started | 7 | 2026-05-22 | 2026-05-27 |  |  | 0%
15 | Painting | Chuo Painting | Not started | 4 | 2026-05-28 | 2026-05-31 |  |  | 0%
16 | Fixture Installation/Test Run | Daiichi Equipment | Not started | 4 | 2026-06-01 | 2026-06-08 |  |  | 0%
17 | Exterior Works/Paving | Sato Civil Works | Not started | 5 | 2026-06-09 | 2026-06-16 |  |  | 0%
18 | Completion review | Supervisor/Owner | Not started | 3 | 2026-06-20 | 2026-06-22 |  |  | 0%
19 | Touch-up | Partner Companies | Not started | 6 | 2026-06-23 | 2026-06-27 |  |  | 0%
20 | Done | General Contractor/Owner | Not started | 2 | 2026-06-30 | 2026-06-30 |  |  | 0%
Status report master details are displayed automatically. Blue "■" indicates Planned, and green "A" indicates Actual. For tasks in progress, Actual progress is shown up to the progress check date.

## Weekly status table
2026/04/13 Weekly status table
Project name | XX Apartment Building Project |  |  |  |  | Week start date | 2026-04-13 |  |  | Planned | Actual | Daily planned crew is calculated automatically
No | Task name | Partner | Crew | Planned start | Planned end | Actual start | Actual end | Priority | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | Notes
[9 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Daily planned crew | [8 empty] | 11 | 11 | 5 | 5 | 8 | 8 | 4
1 | Kickoff prep | Project Alpha | 4 | 2026-04-01 | 2026-04-03 | 2026-04-01 | 2026-04-03 | High | [7 empty] | Pre-start preparation
2 | Setting out/excavation | Project Alpha | 6 | 2026-04-04 | 2026-04-08 | 2026-04-04 | 2026-04-08 | High | [7 empty] | Includes soil disposal
3 | Crushed stone base/lean concrete | Sato Civil Works | 5 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | High
4 | Rebar tying | Tanaka Rebar | 6 | 2026-04-11 | 2026-04-14 | 2026-04-11 | 2026-04-14 | High | 2026-04-13: Actual; 2026-04-14: Actual | Includes rebar inspection
5 | Formwork | Takahashi Formwork | 5 | 2026-04-13 | 2026-04-16 | 2026-04-13 |  | High | Actual | Actual | Actual | Actual | Actual | Actual |  | Partial rework
6 | Design review | Chuo Ready-Mix Concrete | 8 | 2026-04-17 | 2026-04-18 | 2026-04-17 |  | High | 2026-04-17: Actual; 2026-04-18: Actual | Weather Check Required
7 | Demolding/Curing | Takahashi Formwork | 4 | 2026-04-19 | 2026-04-22 |  |  | Medium | 2026-04-19: Planned
8 | 1F Structural Frame | Yamaguchi Project | 10 | 2026-04-23 | 2026-04-30 |  |  | High
9 | Roof Testing | Mizuno Testing | 4 | 2026-05-01 | 2026-05-04 |  |  | Medium
10 | Sash Installation | Suzuki Sash | 4 | 2026-05-06 | 2026-05-10 |  |  | Medium
11 | Electrical Wiring (Rough Wiring) | Toko Electrical | 5 | 2026-05-08 | 2026-05-16 |  |  | Medium
12 | Plumbing/Drainage Pre-piping | Daiichi Equipment | 5 | 2026-05-08 | 2026-05-15 |  |  | Medium
13 | Light Gauge Framing | Project Support | 6 | 2026-05-17 | 2026-05-21 |  |  | Medium
14 | PB Board Installation | Project Support | 7 | 2026-05-22 | 2026-05-27 |  |  | Medium
15 | Painting | Chuo Painting | 4 | 2026-05-28 | 2026-05-31 |  |  | Medium
16 | Fixture Installation/Test Run | Daiichi Equipment | 4 | 2026-06-01 | 2026-06-08 |  |  | High
17 | Exterior Works/Paving | Sato Civil Works | 5 | 2026-06-09 | 2026-06-16 |  |  | Medium
18 | Completion review | Supervisor/Owner | 3 | 2026-06-20 | 2026-06-22 |  |  | High
19 | Touch-up | Partner Companies | 6 | 2026-06-23 | 2026-06-27 |  |  | High
20 | Done | General Contractor/Owner | 2 | 2026-06-30 | 2026-06-30 |  |  | High
Weekly Planned is linked automatically from Status report master. Daily planned crew totals the workers assigned to tasks planned for that day.

## Meeting / delivery status
Meeting / delivery status
Project name | XX Apartment Building Project |  |  |  |  | Record meeting, inspection, and delivery plans
No | Date | Time | Category | Details | Partner companies | Location | Status | Notes
1 | 2026-04-13 | 8:00 | Safety | Weekly project sync | Prime contractor/all subcontractors | Project office | Done | Every Monday
2 | 2026-04-14 | 10:00 | Review | Design check | Supervisor/Tanaka Rebar | Project | Done
3 | 2026-04-17 | 13:00 | Delivery | Ready-mix delivery | Central Ready-Mix | Project | Done | Final pre-pour check
4 | 2026-04-18 | 15:00 | Meeting | Post-pour confirmation for foundation concrete | Prime contractor/Central Ready-Mix | Project | Planned
5 | 2026-05-06 | 9:30 | Delivery | Window frame delivery | Suzuki Windows | External yard | Planned
6 | 2026-06-20 | 10:00 | Review | Completion review | Owner/supervisor | Project | Planned | Confirmation of corrective items
This sheet is a helper table for managing non-task plans such as meetings, inspections, and deliveries.