## Dashboard
Project Tools and Resources Comparison Library
Use this workbook to select project management tools, maintain a resource library, estimate budgets, and plan rollout or migration across organizations and business scenarios. Start in Recommender, then tune the evaluation model in Scoring settings and Tool library.
Tool count | Resource count | Business scenario count | Total weight | Current business scenario | Recommended Top 1 |  |  | Scoring heatmap notes
13 | 20 | 10 | 100 | PMO portfolio governance | Wrike |  |  | The dashboard and tool/scenario sheets use data bars, color scales, and status colors as visual summaries: higher scores move toward green, and cost/TCO inputs display as data bars.
Chart objects are intentionally avoided so the template stays compatible across Excel environments.
Top 8 overall scores |  |  |  | Top 3 recommendations by business scenario
| tool | weighted | Recommended positioning | Business scenario | Top 1 | Top 2 | Top 3
1 | Wrike | 4.2 | Priority shortlist | Small-team task collaboration | Trello | ClickUp | monday.com
2 | Smartsheet | 4.12 | Good for pilot | Agile software development | Wrike | Smartsheet | Jira
3 | monday.com | 3.8 | Good for pilot | PMO portfolio governance | Wrike | Smartsheet | Microsoft Project/Project Online
4 | Asana | 3.8 | Good for pilot | Marketing campaign and creative collaboration | Wrike | Smartsheet | ClickUp
5 | Microsoft Project/Project Online | 3.79 | Good for pilot | Client delivery / consulting services | Wrike | Smartsheet | monday.com
6 | ClickUp | 3.77 | Good for pilot | Construction, engineering, and long-cycle projects | Wrike | Smartsheet | Microsoft Project/Project Online
7 | Jira | 3.7 | Good for pilot | Product launch / cross-functional collaboration | Wrike | Smartsheet | Microsoft Project/Project Online
8 | Airtable | 3.5 | Scenario fit | Resource and time management | Wrike | Smartsheet | Microsoft Project/Project Online
|  |  |  | Knowledge base plus lightweight projects | Notion | ClickUp | monday.com
|  |  |  | Strategic OKR / goal tracking | Wrike | Smartsheet | Microsoft Project/Project Online
Items needing attention | Formula / source | Current value | Recommended action
Weights total 100 | scoringsettings!B16 | 100 | 100，pleaseinscoringsettings 。
Sources needing review | COUNTIFsourcestatus | 18 | Quarterlyreviewtool 、price、securityandIntegration。
Shortlist count | toolstatus | 5 | scenariokeep2-3 can tool。
Pilot tool count | toolstatus | 0 | scoringandrisks。

## Instructions
Project Tools and Resources Comparison Library Template - Instructions
This template supports project management tool selection and resource library governance across organizations and business scenarios. It covers candidate scoring, resource capture, scenario recommendations, budget TCO estimates, and rollout tracking.
Step | Worksheet | Action | Output | Scoring rules
1 | Recommender | enterCompany size、Industry / department、Priority business scenario、Budget sensitivityandexistingecosystem。 | Top 1/2/3 toolrecommendation。 | 5 = Excellent / very strong fit
2 | Scoring settings | bycompanywatch 12 Evaluation dimension ， 100。 | unifiedscoring 。 | 4 = Strong / good fit
3 | Tool library | maintain tool、applicablescenario、source、scoring、statusandnotes。 | can toolcomparisonlibrary。 | 3 = Usable / requires setup
4 | Resource library | maintainTemplate、Method、Training、Community、IntegrationandChecklist。 | project managementresource 。 | 2 = Weak / needs support
5 | Scenario matching | byBusiness scenario ， scenario Top 3 tool。 | differentcompanyanddepartment recommendation。 | 1 = Poor fit / missing
6 | Budget TCO | users、quote、 、implementation 、Integration andTraining 。 | / costestimate。
7 | Rollout plan | tracking 、migration、Training、launchandretrospectivetask。 | roadmap 。
8 | Sources and updates | Quarterlyreview 、price、securityandIntegrationsource。 | toollibraryvalidity。 | applicableBusiness scenario
Small-team task collaboration
Agile software development
Editing tips | Notes |  |  | PMO portfolio governance
Green/yellow cues | priority orcanuse； needs reviewor 。 |  |  | Marketing campaign and creative collaboration
Score columns | toollibraryMedium 12 scoring can ， update 、 andRecommended positioning。 |  |  | Client delivery / consulting services
Source column | do notdeleteSource URL；futurereview 、pricingandsecurityterms can access。 |  |  | Construction, engineering, and long-cycle projects
Quote input | pricechangesquick，budgetTCO defaultblankvendorprice，pleaseaslatestquoteas baseline。 |  |  | Product launch / cross-functional collaboration
Reuse across companies | fordifferentcompanycopyworkbookorcopy“recommendation ” ，keep tool/resourcemaster library can。 |  |  | Resource and time management
Knowledge base plus lightweight projects
Strategic OKR / goal tracking

## Scoring settings
Scoring settings and dropdown options
After weights are adjusted, the tool library, scenario matching, and recommender update automatically. The default weights suit general enterprise project management and can be adapted for governance, agile delivery, resources, or cost focus.
Evaluation dimension | Weight % | Scoring notes | Company size | Project / procurement status | Priority | Business scenario | resourcetype
Ease of use | 12 | 、 costLow、 adoption | Solo / personal | To evaluate | High | Small-team task collaboration | Template
Feature coverage | 13 | task、milestone、views、dependencies、collaboration、approvaland morebasiccapability | Small team | Shortlisted | Medium | Agile software development | Method
Agile / Kanban | 7 | 、Scrum/Sprint、Backlog、agile | Mid-sized company | Pilot | Low | PMO portfolio governance | Training
Gantt / dependencies | 8 | 、 、dependencies、milestonePlanning | Large enterprise | Purchased |  | Marketing campaign and creative collaboration | Community
Resources / capacity | 9 | resourceload、time、availability、roles/ | Group / multi-division | Rejected |  | Client delivery / consulting services | Integration
PMO / portfolio | 8 | projectportfolio、plan 、 、 projectPriority |  | Keep watching |  | Construction, engineering, and long-cycle projects | Document
Reporting dashboards | 9 | progress、status 、executiveviews、can data |  |  |  | Product launch / cross-functional collaboration | Checklist
Automation integration | 8 | automation、API、connectors、andexistingtoolIntegration |  |  |  | Resource and time management | Metric
Documentation knowledge base | 6 | Document、Wiki、meeting 、project |  |  |  | Knowledge base plus lightweight projects | automation
Permissions and security | 8 | permissions、audit、SSO、enterprise 、datasecurity |  |  |  | Strategic OKR / goal tracking | Prompt / AI support
Cost friendliness | 5 | cost、priceflexibility、free/low-cost
Low implementation complexity | 7 | launchquick、configurationlow、migrationandTrainingpressureLow
Total weight | 100 | for 100；ifnotfor 100， by 。

## Tool library
Tool library
Maintain each candidate project management tool, its fit, sources, scores, and recommended positioning. Score columns use 1 to 5, where 5 means stronger or better fit; a higher Low implementation complexity score means easier rollout.
tool | category | Suitable company size | Core business scenarios | Typical strengths | Risks / limitations to watch | Official / reference source | Initial procurement status | License / budget notes | Data residency / security notes | Integration ecosystem notes | Notes / company customization | Ease of use | Feature coverage | Agile / Kanban | Gantt / dependencies | Resources / capacity | PMO / portfolio | Reporting dashboards | Automation integration | Documentation knowledge base | Permissions and security | Cost friendliness | Low implementation complexity | weighted |  | Recommended positioning | Sort helper
Asana | Collaborative work management | Small team; mid-sized company; large enterprise | cross-functionalproject、marketingcampaign、 、projectrequest | task、project、goalandautomation ，fitneeds transparentcollaborationandexecutivevisualization 。 | resourcecapacity/complexPMO needs High or system。 | https://asana.com/features | Shortlisted | byuse subscription；needscheck andHigh plan。 | watchpermissions、SSO、dataregionandaudit 。 | Slack、Google、Microsoft 365、Jiraand more Integration。 | scoring，canbycompany 。 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | 4 | 3 | 4 | 3.8 | 3 | Good for pilot | 3.8
Jira | Agile development / issue tracking | Mid-sized company; large enterprise | Agile software development、ITneeds 、 and management | agile、 /Scrum、 andAtlassianecosystem High。 | development and configurationmayneeds management 。 | https://www.atlassian.com/software/jira/features | Shortlisted | byuse subscription；Marketplace impact cost。 | fitneeds permissions、 andaudit 。 | Confluence、Bitbucket、GitHub、Slack、CI/CDtoolIntegration。 | development/ITscenariopriority 。 | 3 | 4 | 5 | 4 | 3 | 4 | 4 | 4 | 2 | 5 | 3 | 3 | 3.7 | 7 | Good for pilot | 3.7
monday.com | Visual work management | Small team; mid-sized company; large enterprise | marketing、operations、PMO、 /clientproject | 、Templateand / / capability ，fitbusiness quicklybuild。 | complexdependencies、resourceand needsclarifyplanandconfigurationboundaries。 | https://monday.com/partners/projectmanagement | Shortlisted | byuse subscription；automationandIntegration needscheck。 | enterpriseeditionpermissions/ needs 。 | businessSaaS、communicationandautomationtoolconnection broad。 | fit departmentquickly broad。 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | 4 | 3 | 4 | 3.8 | 3 | Good for pilot | 3.8
ClickUp | All-in-one project / knowledge collaboration | Small team; mid-sized company | project、Document、task、 、automationunifiedmanagement | Feature coveragebroad，built-inDocument、views、automationandAIcapability，fit integrate tool 。 | standardizationand important，launchbeforeneedscontrolcomplex 。 | https://clickup.com/teams/project-management | To evaluate | priceflexibility High；needscheckAI、automation、storageand morelimit。 | enterprisepermissions/data needs 。 | andSlack、Google、Microsoft、GitHuband moreconnection。 | Good for pilot 。 | 3 | 5 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 3 | 4 | 3 | 3.77 | 6 | Good for pilot | 3.77
Trello | Lightweight Kanban | Solo / personal; small team | Small-team task collaboration、 / 、lightweight | 、 / / ，fitquicklyInitiation。 | complex 、resource、PMOand capability ，needs or 。 | https://trello.com/tour | To evaluate | free/low-coststart；Power-Upsandautomationlimitneedsconfirm。 | fitlightweightpermissions；enterprise needs Atlassianmanagementcapability。 | Atlassianecosystem、Slack、Googleand moreIntegration。 | lightweightscenarioHigh 。 | 5 | 3 | 5 | 2 | 1 | 2 | 2 | 3 | 2 | 3 | 5 | 5 | 3.13 | 11 | Scenario fit | 3.13
Microsoft Planner | Microsoft 365 task / project management | Small team; mid-sized company; large enterprise | M365intaskcollaboration、departmentproject、basicplantracking | andMicrosoft 365ecosystemnativeIntegration，fit M365 enterprisequicklyadoption。 | complexproject、resourceandportfoliomanagementneedsandProjectcapabilityor toolportfolio。 | https://www.microsoft.com/en-us/microsoft-365/planner/project-management | Shortlisted | andM365plan/Planner tierrelated，needschecklicense。 | Microsoft and capability， needsby 。 | Teams、Outlook、Loop、Power Platformand more。 | M365 priority 。 | 4 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 4 | 4 | 4 | 3.17 | 10 | Scenario fit | 3.17
Microsoft Project/Project Online | Professional project / PPM | Mid-sized company; large enterprise; group / multi-division | plan、resource 、PMO 、projectportfolio | 、resource、portfolioandenterprise capability，fit PMO。 | costandimplementationcomplex High，business collaboration needs 。 | https://learn.microsoft.com/en-us/office365/servicedescriptions/project-online-service-description/microsoft-project-online-service-description | To evaluate | license、implementation、Trainingand costneeds 。 | fitenterprise 、permissionsand Highscenario。 | M365、Power BI、Power Platformand more。 | PMO/complex 。 | 2 | 5 | 3 | 5 | 5 | 5 | 4 | 4 | 2 | 5 | 2 | 2 | 3.79 | 5 | Good for pilot | 3.79
Smartsheet | Spreadsheet-style project / PMO platform | Mid-sized company; large enterprise | PMO、projectportfolio、resource/budget、cross-functionaloperations | + +automation+ portfolio ，fitstandardizationproject 。 | configuration andpermissions needs before ； Mediumand more。 | https://www.smartsheet.com/solutions/project-management | Shortlisted | bylicenseandHigh ；resource/controlMedium and moreneeds 。 | enterprisepermissions、 and fitMedium 。 | Microsoft、Google、Slack、Salesforceand more。 | fitPMOstandardization。 | 3 | 5 | 3 | 5 | 5 | 5 | 5 | 4 | 2 | 5 | 3 | 3 | 4.12 | 2 | Good for pilot | 4.12
Wrike | Enterprise work / resource management | Mid-sized company; large enterprise | PMO、marketingoperations、servicedeliverable、resourcemanagement | resource、 、 、 andenterprise capability 。 | budgetandimplementationconfigurationneeds ； may 。 | https://www.wrike.com/features/ | To evaluate | enterprisecapabilitymayincreasesubscriptionandimplementationcost。 | fit permissions、auditandmanagementvisualization 。 | SaaS、 、communicationandBIIntegration。 | fitcomplex andresourcemanagement。 | 3 | 5 | 4 | 5 | 5 | 5 | 5 | 4 | 3 | 5 | 2 | 3 | 4.2 | 1 | Priority shortlist | 4.2
Notion | Documents / knowledge base plus lightweight projects | Solo / personal; small team; mid-sized company | knowledge base、 /in project、lightweighttask、 Document | Document、datalibraryandprojectviews ，fit andlightweightExecution 。 | PMO、resourceandcomplex capability ，needs Templateandpermissions。 | https://www.notion.com/product/projects | To evaluate | byuse subscription；AIandenterprise needs 。 | permissionstierfit collaboration，complexenterprise needs 。 | Slack、Google、GitHub、Figmaand more。 | fit 。 | 4 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 5 | 3 | 4 | 4 | 3.19 | 9 | Scenario fit | 3.19
Airtable | Low-code database / project operations | Small team; mid-sized company; large enterprise | projectrequest、operations 、resource/in management、 | datalibrary、fields、views、automationand ，fit buildbusiness use。 | project managementneedsbuild ；complex andresourcecapabilityneeds Template/ 。 | https://www.airtable.com/solutions/project-management | To evaluate | byuse /data /automationlimit ，needs 。 | permissions、data andcross-functional needs 。 | API、automation、SaaSconnectorsbroad。 | fit projectoperations。 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | 3.5 | 8 | Scenario fit | 3.5
Basecamp | Simple project / client collaboration | Solo / personal; small team; mid-sized company | clientdeliverable、 collaboration、 project、communication | project、 、 、 、 andclientcollaboration Medium，Action 。 | complex 、resource/portfolio and 。 | https://basecamp.com/ | To evaluate | orplan pricingneeds ，fitcontrol toolcost。 | permissionsandclientcan needs project 。 | can Document/ /tool，lightweightIntegration。 | fit andclientcollaboration。 | 5 | 3 | 3 | 2 | 1 | 2 | 3 | 3 | 3 | 3 | 4 | 5 | 3.09 | 12 | Scenario fit | 3.09
Miro | Visual collaboration / planning whiteboard | Solo / personal; small team; mid-sized company; large enterprise | 、projectPlanning、agile 、visualizationroadmap | 、 、Template、 / and morevisualizationcapability，fit andPlanning。 | notcompletePMOExecutionsystem，needsandtask/projecttoolwork with。 | https://miro.com/project-management/ | Keep watching | byuse subscription；enterprisesecurityandHigh collaboration needs 。 | enterpriseeditionpermissions、SSO、data needs 。 | Asana、Slack、Jiraand moreIntegration。 | forproject managementresource/collaboration value。 | 4 | 3 | 3 | 3 | 1 | 2 | 2 | 4 | 4 | 3 | 4 | 4 | 3.03 | 13 | Scenario fit | 3.03

## Resource library
Resource library
Maintain project management resources such as templates, methods, training, communities, integrations, and checklists. Filter by business scenario, project phase, priority, and owner.
Resource ID | Resource name | type | Project phase | Business scenario | fitCompany size | Usage frequency | Priority | Recommended tool / source | Core purpose | Key fields / outputs | Access / maintenance link | owner | Update cadence | status | notes
R-001 | project Template | Template | Initiation | All projects / initiation approval | All | Every project | High | PMI/ProjectManagement.com | project 、scope、goal、sponsorandsuccesscriteria。 | project 、goal、scope、milestone、 、approval | https://www.pmi.org/insights | PMO | Quarterly | Usable | Initiationphasepriority use。
R-002 | projectplanTemplate | Template | Planning | traditional/hybridproject、clientdeliverable | All | Every project | High | ProjectManagement.com | organizescope、progress、cost、resource、risksandcommunicationintegrateformainplan。 | WBS、progress、budget、quality、risks、communicationplan | https://www.projectmanagement.com/deliverables/973994/project-plan-template | Project manager | Quarterly | Usable | canandtoolMedium projectTemplate 。
R-003 | WBS | Template | Planning | complexdeliverable、engineering、development | Mid-sized company; large enterprise | Every project | High | Smartsheet/Microsoft | organizeoutcomesbreak downforestimable、assignable、trackable work packages。 | deliverable 、work packages、owner、estimatetime | https://www.smartsheet.com/content-center/best-practices/project-management-guide/templates-project-management | Project manager | Quarterly | Usable | fit /resourceplanbefore input。
R-004 | plananddependencies | Template | Planning / execution | long-cycleproject、cross-functional | Mid-sized company; large enterprise | Every project | High | Microsoft/Smartsheet | 、dependencies、milestoneand tracking。 | task、 / 、dependencies、milestone、progress | https://www.microsoft.com/en-ca/microsoft-365/project/project-planning-templates | Program manager |  | Usable | fitandMicrosoft Project/Smartsheet 。
R-005 | agileSprint | Template | Execution | Agile software development、 | All | Weekly / per sprint | High | Jira/Trello/Notion | managementBacklog、Sprint、taskstatusand 。 | Backlog、 、Priority、Sprint、status | https://trello.com/templates/project-management | Scrum Master |  | Usable | development canmigration Jira。
R-006 | RACIresponsibilitymatrix | Template | Planning / execution | cross-functionalcollaboration、PMO | All | Every project | High | PMI/Smartsheet | clarify 、 、consulting、 ， Lowcommunication 。 | task、R/A/C/Iroles、 boundaries | https://www.smartsheet.com/content-center/best-practices/project-management-guide/templates-project-management | Project manager | Quarterly | Usable | fitcomplex project。
R-007 | risks | Template | Monitoring | Highnot project、vendordeliverable | All | Weekly / monthly | High | PMI/ProjectManagement.com | logrisks、 、impact、 andowner。 | risks 、 、impact、and more 、 、status | https://www.projectmanagement.com/templates/ | Project manager |  | Usable | connect to toolautomatically 。
R-008 | issue/blocker | Checklist | Execution / monitoring | All projects | All |  | High | PMI/Smartsheet | trackingissue、blocker、action itemsandresolutiondeadline。 | issue、impact、owner、 、status | https://www.smartsheet.com/content-center/best-practices/project-management-guide/templates-project-management | Project manager |  | Usable | in or toolMediummaintain。
R-009 | projectrequest/needs | Template | Initiation | PMO、marketing、ITservice、operationsneeds | Mid-sized company; large enterprise | Ongoing | High | monday/Airtable/Smartsheet | Medium projectideas、approvalandPriorityinformation。 | request 、businessvalue、budget、Priority、approvalstatus | https://www.airtable.com/solutions/project-management | PMO/operations | Quarterly | Usable | fitLow andautomation。
R-010 | resourcecapacityplan | Template | Planning / monitoring | Resource and time management、PMO | Mid-sized company; large enterprise | Weekly / monthly | High | Smartsheet/ProjectManagement.com | Monitoringpeopleavailability、allocation rateandbottleneck。 | resource、roles、canusetime、 time、utilization | https://www.smartsheet.com/resource-planning-templates | Resource manager |  | Usable | complexscenarioconnect toWrike/Project。
R-011 | budgetandTCO | Template | Planning / procurement | toolprocurement、projectbudgetcontrol | All | Per procurement / quarterly | High | Built in | license、implementation、Integration、Trainingandmaintaincost。 | users、 、 、implementation 、Integration 、Training | Built in: Budget TCO sheet | Procurement / Finance | Quarterly | Usable | Already built into this template.
R-012 | projectstatus | Template | Monitoring | executive 、clientdeliverable | All | Weekly / monthly | High | PMI/ProjectManagement.com | unifiedOutputprogress、risks、blocker、budgetand 。 | RAGstatus、milestone、risks、budget、decisionrequest | https://www.projectmanagement.com/templates/ | Project manager |  | Usable | fit automatically 。
R-013 | changerequestTemplate | Template | Monitoring | scope/budget/ change | All | As needed | High | PMI/Smartsheet | change scope、 、cost、qualityandresource impact。 | changenotes、impact 、approval、implementationplan | https://www.pmi.org/insights | Project manager | Quarterly | Usable | 。
R-014 | communicationplan | Template | Planning / execution | cross-functional/clientproject | All | Every project | Medium | PMI/ProjectManagement.com | communicationobject、 、 、in andowner。 | 、watch 、 、 、owner | https://www.projectmanagement.com/templates/ | Project manager | Quarterly | Usable | canandRACIlink。
R-015 | retrospective/lessons Template | Template | Closure | All projects | All | Every project | Medium | PMI/Notion | issue、successlessons、can use and 。 | facts、causes、lessons、action items、owner | https://www.notion.com/templates/category/projects | Project manager | Quarterly | Usable | fit knowledge base。
R-016 | projectportfolio | Metric | Monitoring | PMO、executive | Mid-sized company; large enterprise | Weekly / monthly | High | Smartsheet/Wrike/Asana | projecthealth、progress、budget、risksandresource use。 | project、RAG、progress、budget、risks、resource | https://www.smartsheet.com/solutions/project-management | PMO |  | Usable | canintoolMediumbuildorconnectionBI。
R-017 | vendor matrix | Template | Procurement / evaluation | tool 、 service | All | As needed | High | Built in | 、cost、security、serviceandimplementationrisks。 | scoring 、 、vendor、scoring、risks | Built in: Tool library / Scoring settings | Procurement / PMO | Quarterly | Usable | Already built into this template.
R-018 | AIprojectsummarypromptlibrary | Prompt / AI support | Execution / monitoring | meetingsummary、status 、risksidentification | All |  | Medium | ClickUp/Asana/Miro/Airtable | useAI meeting 、 action itemsandrisks 。 | input 、Output 、 、 usescope | https://miro.com/ai/project-management/ | Project manager |  | To complete | datasecurityandsensitivityinformation。
R-019 | projectknowledge base Template | Document | Full life cycle | 、 /in | Solo / personal; small team; mid-sized company | Ongoing | Medium | Notion/Basecamp | organizeproject 、decision、meeting、 andretrospectiveunified 。 | projectmain 、meeting 、decision 、 | https://www.notion.com/product/projects | Team lead | Quarterly | Usable | fitNotion/Basecamp/Confluence。
R-020 | clientdeliverableacceptance | Checklist | Closure | consulting、 、implementationdeliverable | Small team; mid-sized company | Every project | High | Basecamp/PMI | confirmdeliverable 、client 、approval、 and 。 | deliverable 、acceptancecriteria、approval 、open items | https://basecamp.com/learn | Client manager | Quarterly | Usable | fitclientcollaborationscenario。

## Scenario matching
Business scenario matching matrix
Each business scenario uses its own weights and matches them against Tool library scores to return the Top 3 recommended tools. Adjust scenario weights for organization type, industry, and project maturity.
Business scenario | Scenario notes | Ease of use | Feature coverage | Agile / Kanban | Gantt / dependencies | Resources / capacity | PMO / portfolio | Reporting dashboards | Automation integration | Documentation knowledge base | Permissions and security | Cost friendliness | Low implementation complexity | Total weight | Top 1 | Top 2 | Top 3 | Asana | Jira | monday.com | ClickUp | Trello | Microsoft Planner | Microsoft Project/Project Online | Smartsheet | Wrike | Notion | Airtable | Basecamp | Miro
Small-team task collaboration | lightweightproject、 collaboration、 needscomplex ，focus quickandcostLow。 | 14 | 10 | 12 | 5 | 2 | 2 | 5 | 8 | 10 | 5 | 13 | 14 | 100 | Trello | ClickUp | monday.com | 3.75 | 3.54 | 3.75 | 3.75 | 3.8 | 3.34 | 3.1 | 3.56 | 3.65 | 3.57 | 3.42 | 3.58 | 3.48
Agile software development | needs 、 、Sprint、 and toolIntegration，focus agileand 。 | 8 | 10 | 20 | 6 | 5 | 8 | 10 | 10 | 3 | 10 | 4 | 6 | 100 | Wrike | Smartsheet | Jira | 3.88 | 4.01 | 3.88 | 3.81 | 3.39 | 3.2 | 3.77 | 4.05 | 4.24 | 3.11 | 3.48 | 3.08 | 3.03
PMO portfolio governance | projectvisualization、resource、budget、portfolioPriorityand ，focus management。 | 4 | 11 | 4 | 11 | 13 | 18 | 13 | 7 | 2 | 11 | 3 | 3 | 100 | Wrike | Smartsheet | Microsoft Project/Project Online | 3.82 | 3.88 | 3.82 | 3.8 | 2.58 | 3.06 | 4.36 | 4.59 | 4.62 | 2.83 | 3.46 | 2.62 | 2.62
Marketing campaign and creative collaboration | campaignplan、in approval、creative and collaboration，focus visualizationand 。 | 12 | 10 | 8 | 10 | 5 | 5 | 10 | 10 | 10 | 6 | 6 | 8 | 100 | Wrike | Smartsheet | ClickUp | 3.79 | 3.63 | 3.79 | 3.79 | 3.23 | 3.17 | 3.56 | 3.92 | 4.04 | 3.36 | 3.48 | 3.21 | 3.21
Client delivery / consulting services | clientproject、deliverable 、acceptance、communicationlogand tracking，focus transparentcollaboration。 | 12 | 10 | 8 | 10 | 8 | 8 | 10 | 7 | 7 | 8 | 6 | 6 | 100 | Wrike | Smartsheet | monday.com | 3.79 | 3.7 | 3.79 | 3.76 | 3.13 | 3.17 | 3.74 | 4.08 | 4.17 | 3.22 | 3.47 | 3.08 | 3.04
Construction, engineering, and long-cycle projects | complex 、dependencies、resourceandmilestone，focus 、resourceandportfolio 。 | 5 | 11 | 3 | 19 | 14 | 14 | 11 | 5 | 2 | 9 | 3 | 4 | 100 | Wrike | Smartsheet | Microsoft Project/Project Online | 3.81 | 3.82 | 3.81 | 3.79 | 2.56 | 3.05 | 4.36 | 4.59 | 4.61 | 2.88 | 3.41 | 2.6 | 2.66
Product launch / cross-functional collaboration | development、 、 、operations ，focus milestone、dependenciesandstatusvisualization。 | 10 | 11 | 10 | 11 | 8 | 10 | 10 | 8 | 5 | 8 | 3 | 6 | 100 | Wrike | Smartsheet | Microsoft Project/Project Online | 3.84 | 3.81 | 3.84 | 3.79 | 3.06 | 3.14 | 3.9 | 4.19 | 4.31 | 3.11 | 3.47 | 2.98 | 2.96
Resource and time management | peoplecapacity、load、utilizationandbottleneckmanagement，focus resourceand 。 | 5 | 9 | 3 | 9 | 23 | 14 | 13 | 5 | 2 | 9 | 3 | 5 | 100 | Wrike | Smartsheet | Microsoft Project/Project Online | 3.72 | 3.72 | 3.72 | 3.67 | 2.48 | 2.97 | 4.31 | 4.57 | 4.59 | 2.8 | 3.41 | 2.54 | 2.47
Knowledge base plus lightweight projects | Document、datalibrary、taskandretrospectiveunified ，focus managementand quick。 | 14 | 8 | 8 | 5 | 2 | 2 | 5 | 7 | 19 | 5 | 11 | 14 | 100 | Notion | ClickUp | monday.com | 3.68 | 3.34 | 3.68 | 3.73 | 3.59 | 3.23 | 2.98 | 3.42 | 3.58 | 3.73 | 3.39 | 3.56 | 3.54
Strategic OKR / goal tracking | projectconnectiongoal、executiveviews、portfolioPriorityandprogresstransparent，focus goaland 。 | 7 | 11 | 5 | 7 | 7 | 17 | 17 | 9 | 5 | 7 | 3 | 5 | 100 | Wrike | Smartsheet | Microsoft Project/Project Online | 3.85 | 3.8 | 3.85 | 3.85 | 2.8 | 3.1 | 4.04 | 4.36 | 4.43 | 3.01 | 3.51 | 2.89 | 2.81

## Recommender
enterpriseprofilerecommendation
After selecting company size, business scenario, and budget sensitivity, the section below reads recommended tools from Scenario matching and pulls scores, positioning, strengths, risks, and sources from Tool library.
Input item | Enter / select | Notes | Maintenance advice
Company name | Acme Operations Inc. | use in log，not and 。 | by company/ nameupdate。
Company size | Mid-sized company | impact ；futurecan for 。 | fromdropdownoptionsselect。
Industry / department | General / PMO | canentersoftware、 、marketing、consulting、engineeringand more。 | use notesand 。
Priority business scenario | PMO portfolio governance | recommendation 。 | scenario，cancopy or scenario 。
Budget sensitivity | Mediumsensitivity | use procurement andTCO 。 | budgetTCO 。
Existing ecosystem / constraints | Microsoft 365; Slack | enterexistingtool、SSO、data 、securityand moreconstraints。 | use 。
Recommendation item | Top 1 | Top 2 | Top 3
Recommended tool | Wrike | Smartsheet | Microsoft Project/Project Online
Overall score | 4.2 | 4.12 | 3.79
Recommended positioning | Priority shortlist | Good for pilot | Good for pilot
Typical strengths | resource、 、 、 andenterprise capability 。 | + +automation+ portfolio ，fitstandardizationproject 。 | 、resource、portfolioandenterprise capability，fit PMO。
Risks / limitations to watch | budgetandimplementationconfigurationneeds ； may 。 | configuration andpermissions needs before ； Mediumand more。 | costandimplementationcomplex High，business collaboration needs 。
referencesource | https://www.wrike.com/features/ | https://www.smartsheet.com/solutions/project-management | https://learn.microsoft.com/en-us/office365/servicedescriptions/project-online-service-description/microsoft-project-online-service-description
Next actions | Notes | owner | Due date
1. Hold requirements interviews | confirmBusiness scenario、constraints、existingsystemand 。 | PMO / business owner
2. Adjust scoring weights | in“scoringsettings”and“scenario ”Medium 。 | PMO
3. Create the shortlist | select 2-3 tool vendor or 。 | Procurement / PMO
4. Enter TCO | inbudgetTCO quote、implementation 、Training 。 | Procurement / Finance
5. Pilot retrospective | logadoption 、 、risksandlaunch 。 | Project manager

## Budget TCO
Budget and TCO estimate
Enter vendor quotes, users, fixed fees, implementation, integration, and training costs to calculate first-year and following-year cost automatically. Pricing changes quickly, so use formal vendor quotes for decisions.
tool | users | Monthly price / user | Fixed monthly fee | One-time implementation cost | Integration development cost | Training cost | Annual license | First-year total cost | Following-year annual cost | Cost notes / currency | Quote / source link | notes
Asana | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://asana.com/features
Jira | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://www.atlassian.com/software/jira/features
monday.com | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://monday.com/partners/projectmanagement
ClickUp | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://clickup.com/teams/project-management
Trello | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://trello.com/tour
Microsoft Planner | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://www.microsoft.com/en-us/microsoft-365/planner/project-management
Microsoft Project/Project Online | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://learn.microsoft.com/en-us/office365/servicedescriptions/project-online-service-description/microsoft-project-online-service-description
Smartsheet | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://www.smartsheet.com/solutions/project-management
Wrike | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://www.wrike.com/features/
Notion | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://www.notion.com/product/projects
Airtable | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://www.airtable.com/solutions/project-management
Basecamp | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://basecamp.com/
Miro | 50 |  | 0 |  |  |  | 0 | 0 | 0 | Use one reporting currency, such as USD or local currency. | https://miro.com/project-management/

## Rollout plan
Rollout and migration plan
Use this plan to move from selection into pilot, launch, training, and retrospective. Adjust dates, owners, status, and outputs to match the company cadence.
phase | Key task | owner | Start date | End date | Duration (days) | status | Priority | Dependencies / prerequisites | Output / acceptance | Risk point | notes
Evaluation preparation | confirm goal、scope、budget and 。 | PMO | 2026-05-01 | 2026-05-03 | 3 | Not started | High | Business sponsor | Selection charter / review plan | goalnot scope
Requirements interviews | business、IT、security、financeand Project manager。 | PMO / business | 2026-05-04 | 2026-05-10 | 7 | Not started | High | Evaluation preparation | Requirements list / must-haves | needs Priority
Weight adjustment | based onneeds updatescoringsettingsandscenario 。 | PMO | 2026-05-11 | 2026-05-13 | 3 | Not started | High | Requirements interviews | Confirmed scoring model | not
Initial candidate tool screening | 3-5 tool Vendor material。 | Procurement / PMO | 2026-05-14 | 2026-05-18 | 5 | Not started | High | Weight adjustment | Shortlisted | informationnotcomplete
Security / legal review | SSO、permissions、data 、DPA、auditand more 。 | IT / Legal | 2026-05-19 | 2026-05-26 | 8 | Not started | High | Initial candidate tool screening | Security review notes | cycle
Pilot setup | configuration 、Template、fields、rolesandbasicautomation。 | Tool administrator | 2026-05-27 | 2026-06-05 | 10 | Not started | Medium | Security review | Pilot environment | configurationimpact
Data migration plan | existingproject、task、Document、permissionsand datamigration 。 | IT/PMO | 2026-05-27 | 2026-06-08 | 13 | Not started | Medium | Pilot setup | Migration list / scripts | dataqualityorpermissions
Integration testing | andSSO、 、 、 、BIordevelopmenttoolconnection。 | IT | 2026-06-06 | 2026-06-15 | 10 | Not started | Medium | Pilot setup | Test report | Integrationlimitimpact
Training and launch communication | prepareTrainingmaterials、FAQ、 projectandchangecommunication。 | PMO/HR | 2026-06-12 | 2026-06-20 | 9 | Not started | High | Pilot setup | Training completion record | adoption not
Full launch | bydepartment/project launch，trackingadoption andissue。 | PMO / business owner | 2026-06-21 | 2026-07-05 | 15 | Not started | High | Training completed | Launch report | resourcenot
Effectiveness retrospective | retrospective 、cost、satisfaction、dataqualityandfuture roadmap。 | PMO | 2026-07-06 | 2026-07-15 | 10 | Not started | Medium | Full launch | Retrospective report / optimization list | Metric

## Sources and updates
Source and update log
External sources are recorded as plain-text URLs for review. Review tool features, pricing, security, and integration information every quarter.
category | Object / tool / resource | Notes | Source URL | Source type | Collection date | Review cadence | status | notes
Evaluation framework | PMIsoftware | project managementsoftwareneeds needs 、watch andEase of use。 | https://www.pmi.org/learning/library/guideline-evaluate-project-management-software-4629 | PMI article | 2026-04-29 | Quarterly | Needs review | use scoring 。
Resource library | PMITemplateandinsights | project managementTemplate、toolandinsightsresource。 | https://www.pmi.org/insights | PMI resources | 2026-04-29 | Quarterly | Needs review | use Resource library。
Resource library | ProjectManagement.comTemplate | Template、projectplan、ChecklistandCommunityresource。 | https://www.projectmanagement.com/templates/ | PMI community | 2026-04-29 | Quarterly | Needs review | use Resource library。
Resource library | SmartsheetprojectTemplate | project management、resourcePlanning、budgetand Template。 | https://www.smartsheet.com/content-center/best-practices/project-management-guide/templates-project-management | Vendor material | 2026-04-29 | Quarterly | Needs review | use Resource library。
Resource library | MicrosoftprojectplanTemplate | projectplanTemplatestrengthsand usescenario。 | https://www.microsoft.com/en-ca/microsoft-365/project/project-planning-templates | Vendor material | 2026-04-29 | Quarterly | Needs review | use Resource library。
Tool official site | Asana | project management、 、goal、 、resourceandsecurity 。 | https://asana.com/features | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Jira | agile、plan、tracking、 andproject management 。 | https://www.atlassian.com/software/jira/features | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | monday.com | project management、 、Planning、trackingand capability。 | https://monday.com/partners/projectmanagement | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | ClickUp | project、Document、 、AIandautomationcapability。 | https://clickup.com/teams/project-management | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Trello | 、 、 andlightweightproject management。 | https://trello.com/tour | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Microsoft Planner | Microsoft 365Mediumtaskandproject managementcapability。 | https://www.microsoft.com/en-us/microsoft-365/planner/project-management | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Microsoft Project Online | projectportfolio、projectandresourcemanagementcapabilitynotes。 | https://learn.microsoft.com/en-us/office365/servicedescriptions/project-online-service-description/microsoft-project-online-service-description | Official documentation | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Smartsheet | projectPlanning、resource、budget、 andautomation。 | https://www.smartsheet.com/solutions/project-management | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Wrike | 、resourceplan、 、 andenterprise management。 | https://www.wrike.com/features/ | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Notion | projectdatalibrary、views、dependencies、taskandprogress 。 | https://www.notion.com/product/projects | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Airtable | project 、fields、automation、 andLow capability。 | https://www.airtable.com/solutions/project-management | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Basecamp | project、 、 、 、clientcollaborationand 。 | https://basecamp.com/ | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。
Tool official site | Miro | 、 、 、 andprojectcollaboration。 | https://miro.com/project-management/ | Tool official site | 2026-04-29 | Quarterly | Needs review | use toolscoring。