## Instructions
Sisendkvaliteedi kontrolli logi mall
Tasuta Exceli mall saabuvate partiide, kontrollitulemuste, erandite järeltegevuse ja ajaloo korraldamiseks ühes töövihikus. Näidisread saab üle kirjutada ja vajaduse järgi ridu lisada.
How to use
1 | Record incoming lots | Enter each supplier lot, sample size, judgment, disposition, and review status in the incoming inspection log.
2 | Detail inspected characteristics | Use the item detail sheet for dimensions, appearance, documents, packaging, and functional checks.
3 | Follow nonconformance to closure | Track root cause, corrective action, due date, verification, and supplier response until closure.
Workbook legend
Input cells | Operational teams overwrite sample rows with actual inspection data.
Computed cells | Supplier summary formulas refresh from the incoming inspection log.
Review cells | Use review status, risk level, and action status to drive follow-up.
linked_sheets
sheet_id | sheet_name | kind | module_id
dashboard | Dashboard | table | dashboard
incoming_inspections | Incoming Inspection Log | table | incoming_inspections
inspection_items | Inspection Item Details | table | inspection_items
nonconformance_actions | Nonconformance Actions | table | nonconformance_actions
supplier_summary | Supplier Summary | table | supplier_summary
inspection_standards | Inspection Standards | table | inspection_standards
master_data | Master Data | table | master_data
sources_versions | Sources and Versions | table | sources_versions

## Dashboard
Dashboard
Tasuta Exceli mall saabuvate partiide, kontrollitulemuste, erandite järeltegevuse ja ajaloo korraldamiseks ühes töövihikus. Näidisread saab üle kirjutada ja vajaduse järgi ridu lisada.
Metric | Current value | Description | Watch rule
Open actions | 2 | Supplier actions still need closure. | Review daily until closed
Incoming pass rate | 50% | Pass rate across sampled incoming lots. | Escalate below target

## Incoming Inspection Log
Incoming Inspection Log
Tasuta Exceli mall saabuvate partiide, kontrollitulemuste, erandite järeltegevuse ja ajaloo korraldamiseks ühes töövihikus. Näidisread saab üle kirjutada ja vajaduse järgi ridu lisada.
Record ID | Inspection date | Item code | Item name | Supplier | Lot number | Sample size | Accepted quantity | Rejected quantity | Auto decision | Disposition | Inspector | Review date | Status | Notes
IQI-2026-0001 | 2026-05-01 | MAT-001 | Aluminum profile | Asahi Materials | AL20260501 | 80 | 80 | 0 | Pass | Release | Taro Sato | 2026-05-01 | Closed | Dimensions and appearance passed.
IQI-2026-0002 | 2026-05-02 | PKG-014 | Printed carton | Harbor Packaging | PKG20260501 | 125 | 122 | 3 | Action needed | Sort before receiving | Michael Chen | 2026-05-03 | In progress | Print offset requires sorting and supplier response.
IQI-2026-0003 | 2026-05-03 | ELE-208 | Chip resistor | Delta Electronics | ELE20260502 | 200 | 195 | 5 | Fail | Reject and return | Taro Sato | 2026-05-04 | Waiting for supplier | Functional sampling exceeded the AQL limit.
IQI-2026-0004 | 2026-05-04 | FAST-030 | Fastener set | Asahi Materials | FAST20260504 | 50 | 50 | 0 | Pass | Release | Michael Chen | 2026-05-04 | Closed | Certificate and count confirmed.

## Inspection Item Details
Inspection Item Details
Tasuta Exceli mall saabuvate partiide, kontrollitulemuste, erandite järeltegevuse ja ajaloo korraldamiseks ühes töövihikus. Näidisread saab üle kirjutada ja vajaduse järgi ridu lisada.
Record ID | Inspection record ID | Item no. | Characteristic | Standard requirement | Inspection method | Measured value | Result | Defect description | Severity | Notes
ITEM-001 | IQI-2026-0001 | 1 | Dimension | Drawing tolerance | Caliper | OK | Pass |  | None | No exception.
ITEM-002 | IQI-2026-0002 | 1 | Printing | Label position and clarity | Visual check | 3/125 | Action needed | Carton print offset | Minor | Sorting required before receiving.

## Nonconformance Actions
Nonconformance Actions
Tasuta Exceli mall saabuvate partiide, kontrollitulemuste, erandite järeltegevuse ja ajaloo korraldamiseks ühes töövihikus. Näidisread saab üle kirjutada ja vajaduse järgi ridu lisada.
Record ID | Inspection record ID | Defect summary | Root cause | Corrective action | Owner | Due date | Action status | Completed date | Verification result | Notes
NCA-001 | IQI-2026-0002 | Carton print offset | Process setting drift | Sort affected cartons and submit improvement report. | Supplier quality engineer | 2026-05-08 | In progress |  | Pending verification | Supplier reply due this week.
NCA-002 | IQI-2026-0003 | Functional sampling failure | Supplier process issue | Return the lot and request 8D plus replenishment plan. | Supplier quality engineer | 2026-05-09 | Waiting for supplier |  | Pending verification | Replacement plan required.

## Supplier Summary
Supplier Summary
Tasuta Exceli mall saabuvate partiide, kontrollitulemuste, erandite järeltegevuse ja ajaloo korraldamiseks ühes töövihikus. Näidisread saab üle kirjutada ja vajaduse järgi ridu lisada.
Supplier | Total lots | Passed lots | Defect lots | Open actions | Pass rate | Risk level | Owner | Latest inspection date
Asahi Materials | 2 | 2 | 0 | 0 | 114 | Low | Taro Sato | 114
Harbor Packaging | 1 | 0 | 1 | 1 | 114 | Medium | Michael Chen | 114
Delta Electronics | 1 | 0 | 1 | 1 | 114 | High | Taro Sato | 114

## Inspection Standards
Inspection Standards
Tasuta Exceli mall saabuvate partiide, kontrollitulemuste, erandite järeltegevuse ja ajaloo korraldamiseks ühes töövihikus. Näidisread saab üle kirjutada ja vajaduse järgi ridu lisada.
Standard ID | Category | Standard name | Acceptance rule | Sample rule | Version | Owner
STD-IQC-001 | Dimension | Dimensional inspection standard | Measure critical dimensions against drawing tolerance. | AQL 1.0 sampling | v1.3 | Quality team
STD-IQC-002 | Packaging | Packaging appearance standard | Labels must be clear and aligned. | Visual sampling | v1.1 | Quality team

## Master Data
Master Data
Tasuta Exceli mall saabuvate partiide, kontrollitulemuste, erandite järeltegevuse ja ajaloo korraldamiseks ühes töövihikus. Näidisread saab üle kirjutada ja vajaduse järgi ridu lisada.
Code | Type | Display name | Sort order | Active | Notes
STATUS_PASS | Status | Pass | 10 | Yes | Released lots can be received.
STATUS_ACTION | Status | Action needed | 20 | Yes | Action owner must be assigned.
STATUS_FAIL | Status | Fail | 30 | Yes | Use for lots rejected or returned.

## Sources and Versions
Sources and Versions
Tasuta Exceli mall saabuvate partiide, kontrollitulemuste, erandite järeltegevuse ja ajaloo korraldamiseks ühes töövihikus. Näidisread saab üle kirjutada ja vajaduse järgi ridu lisada.
Source ID | Document name | Version | Effective date | Owner | Change note
SRC-001 | Incoming inspection standard | 2026.05 | 2026-05-01 | Quality team | Updated sample plan and disposition wording.
SRC-002 | Supplier quality rule | 2026.04 | 2026-04-15 | Supplier quality engineer | Aligned supplier response cycle.