## Instructions
Quality Improvement Record Template ¦ Instructions
Centralize improvement proposals, execution status, root-cause actions, effectiveness checks, and review history for manufacturing, services, software, supply chain, project management, customer complaints, safety, and environmental work.
Worksheet | Purpose | Main input | Main output | Suggested maintenance frequency | Applicable role | Editable | Notes
Improvement Dashboard | Summarizes key metrics, status mix, priority mix, business scenario mix, and monthly new items | No manual input required | Risk alerts and progress visibility | Weekly | Manager / quality owner | Formula areas should not be edited | Automatically reads the improvement log
Improvement Log | Registers every quality improvement item from proposal to confirmation | Theme, issue, metric, owner, status, planned dates, verification result | Overdue days, closure cycle, status prompt | Any time | All submitters / improvement owners | Editable input columns | Yellow columns are suggested inputs
Root Cause Actions | Breaks each improvement item into root cause analysis and action items | Linked ID, action description, responsible owner, deadline, verification method | Action overdue days, completion cycle, benefit variance | Weekly | Improvement owner / executor | Editable input columns | Matches the improvement ID

## Improvement Dashboard
Improvement Dashboard
Centralize improvement proposals, execution status, root-cause actions, effectiveness checks, and review history for manufacturing, services, software, supply chain, project management, customer complaints, safety, and environmental work.
New items this year | Count | Watch list | Theme | Owner | Status | Planned finish | Overdue days
Jan | 0 | Filter overdue, urgent, or high-priority items from Improvement Log and paste them here for weekly meeting follow-up.
Feb | 0
Mar | 0

## Improvement Log
Improvement Log
Centralize improvement proposals, execution status, root-cause actions, effectiveness checks, and review history for manufacturing, services, software, supply chain, project management, customer complaints, safety, and environmental work.
ID | Registered date | Company / site | Department | Business scenario | Improvement theme | Issue / opportunity description | Source channel | Object / product / process | Severity | Priority | Current metric | Target metric | Root cause category | Root cause notes | Owner | Partner department | Status | Planned start | Planned finish | Actual finish | Verification required | Verification owner | Verification date | Effectiveness check | Standardization / prevention | Evidence link / photo | Risk / impact | Notes | Overdue days
QI-0001 | 2026-04-18 | Plant A | Production | Manufacturing | Reduce assembly line rework | Assembly line A has recently exceeded the rework target, mainly because fasteners were missed. | Quality inspection | Assembly line A | Major | High | Rework rate 4.8% | <=2.5% | Method | Work standard updates lag behind, and first-piece confirmation records are incomplete. | Olivia Carter | Quality | In progress | 2026-04-19 | 2026-05-10 |  | Yes | Daniel Brooks |  | Not verified | Update the SOP and add first-piece confirmation checks. | Link / photo ID | Affects delivery cycle and cost | Sample, can be replaced | 0
QI-0002 | 2026-04-19 | Head office | Sales support | Customer complaints | Shorten customer complaint response time | Customer feedback responses exceed the committed time and escalations are increasing. | Customer feedback | After-sales service process | Moderate | Medium | Average response 18 hours | <=8 hours | Management | Complaint assignment rules are unclear, and cross-team confirmation is slow. | Sophia Reed | Operations | To verify | 2026-04-20 | 2026-04-28 | 2026-04-27 | Yes | Ethan Clark | 2026-05-01 | Partly effective | Set up a complaint SLA dashboard and define escalation points. | CRM ticket screenshot | Customer satisfaction decline | Sample, can be replaced | 4
QI-0003 | 2026-04-20 | Remote team | IT | Software and systems | Reduce system release rollbacks | Configuration omissions after release caused temporary rollbacks. | Data analysis | Release process | Major | High | Rollback rate 12% | <=3% | Information system | The change checklist does not cover configuration items, and automated checks are insufficient. | Maya Collins | R&D | Approved | 2026-04-25 | 2026-05-18 |  | Yes | Noah Bennett |  | Not verified | Add a pre-release automated checklist. |  | Affects business continuity | Sample, can be replaced | 0

## Root Cause Actions
Root Cause Actions
Centralize improvement proposals, execution status, root-cause actions, effectiveness checks, and review history for manufacturing, services, software, supply chain, project management, customer complaints, safety, and environmental work.
Action ID | Linked improvement ID | Action type | Action description | Expected output | Owner | Partner / department | Priority | Status | Planned start | Planned finish | Actual finish | Verification method | Verification result | Cost / input | Savings / benefit | Evidence link | Risk / dependency | Notes | Overdue days | Completion cycle in days | Benefit minus input | Status prompt
ACT-0001 | QI-0001 | Standardization | Update the assembly line A work instruction and include it in pre-shift briefing. | New SOP released and acknowledged | Olivia Carter | Production | High | In progress | 2026-04-19 | 2026-05-03 |  | Site sampling plus rework rate comparison | Not verified | 3,000 | 12,000 | SOPLink | Insufficient operator training time | Sample, can be replaced | 0 |  | 9,000 | Follow up
ACT-0002 | QI-0001 | Preventive action | Add a first-piece confirmation form and daily checks. | First-piece confirmation record completeness >=98% | Daniel Brooks | Quality | High | In progress | 2026-04-20 | 2026-05-10 |  | Record sampling | Not verified | 1,000 | 8,000 | Check sheet link |  | Sample, can be replaced | 0 |  | 7,000 | Follow up
ACT-0003 | QI-0002 | System optimization | Add complaint SLA reminders and auto-escalation rules in CRM. | Automatic reminder before timeout | Sophia Reed | IT | Medium | To verify | 2026-04-20 | 2026-04-27 | 2026-04-27 | Ticket data review | Partly effective | 2,000 | 6,000 | CRMScreenshot | Rules need confirmation by Operations | Sample, can be replaced | 5 | 7 | 4,000 | Overdue

## Review and Settings
Review and Settings
Centralize improvement proposals, execution status, root-cause actions, effectiveness checks, and review history for manufacturing, services, software, supply chain, project management, customer complaints, safety, and environmental work.
Review ID | Review date | Linked improvement ID | Review type | Participants | Review focus / issue | Achievement | Lessons learned | Follow-up action | Owner | Next review date | Conclusion / approval status | Notes | Status | Priority | Severity | Business scenario | Source channel | Root cause category | Department | Column21 | Yes / no | Verification result | Column24 | Action type | Column26 | Company / site | Risk level
REV-0001 | 2026-05-01 | QI-0002 | Stage review | Sophia Reed;Ethan Clark;Operations | Whether complaint response SLA improved | Response time has decreased, but escalation rules still need refinement. | System reminders are effective, but cross-team ownership boundaries need more clarity. | Add the escalation matrix and review again in one week | Sophia Reed | 2026-05-08 | Conditionally passed | Sample, can be replaced | New | Low | Minor | Manufacturing | Internal audit | People | Quality | Olivia Carter | Yes | Not verified | Weekly review | Immediate correction | Passed | Head office | Low
REV-0002 | 2026-05-02 | QI-0004 | Closure review | Emma Parker;Quality;Procurement | Whether incoming lot variation was closed | Consecutive lots meet inspection requirements. | Supplier process parameter monthly reports can reveal variation earlier. | Include in monthly supplier evaluation | Emma Parker | 2026-06-02 | Passed | Sample, can be replaced | To evaluate | Medium | Moderate | Service delivery | Customer feedback | Equipment | Production | Daniel Brooks | No | Effective | Monthly review | Root cause analysis | Conditionally passed | Plant A | Medium
review_settings_003 | [12 empty] | Approved | High | Major | Software and systems | Employee suggestion | Material | Operations | Sophia Reed |  | Partly effective | Stage review | Long-term correction | Returned for more detail | Plant B | High