## Шаблон за финансов отчет за при
JSA Job Safety Analysis & Work Permit Checklist Instructions
This operational template is designed for conducting Job Safety Analysis (JSA) prior to high-risk activities such as hot work, work at height, excavation, and confined space entry, and issuing/approving work permits after verifying checklist compliance at the site.
4 Operational Steps
№ | Как да се попълва | Разходи за НИРД
1 | Step 1: [Setup Staff & Master] | Register necessary information in 'Master Settings' and 'Worker List' to organize qualification status.
2 | Step 2: [Job Safety Analysis (JSA)] | In the 'JSA Sheet' sheet, identify hazards for each step, and evaluate initial and residual risks linked to the Risk Matrix.
3 | Step 3: [Fill Permit Checklist] | In the 'Permit Checklist' sheet, check the inspection items (hot work, high place, confined space, etc.) corresponding to the work type and enter 'Yes / No'.
4 | Step 4: [Issue and Track Permits] | In the 'Permit Register', the system automatically checks compliance (if all items conform) and tracks progress from approval to completion.
Cell Color Legend
Категория работа | Color | Description / Usage
Клетка за въвеждане | Light Blue #E6F0FA | Direct input for dates, IDs, text, and numeric values.
Selection (Dropdown) Cell | Light Green #EAF7EA | Dropdown selection for status, work types, verification results, etc.
Formula / Auto Calculation Cell | Uncolored / White | Automatically calculated cells for compliance results, risk scores, and ranks.

## Табло за управление
Табло за управление
Overview of today's work permit status, active high-risk jobs, and pending approval status.
Permits Issued Today |  | Active Jobs |  | Pending Permits |  | Checklist Non-conformances
Breakdown by Work Type
Work Type | Total Cases | Връзка / автоматично отразяване | Очаква одобрение
Hot Work
Work at Height
Confined Space
Изкопни работи
Други
Active Work List by Location
Permit No. | Управление | Contractor/Company | Job Title | Work Type | Период | Централен строителен проект

## Permit Register
Permit No. | Дата на издаване | Work Period (Start to End) | Contractor / Company | Job Title | Управление | Work Type | JSA Ref ID | Checklist Compliance | Статус на одобрение | Одобряващ | Забележки
PT-2026-001 | 2026-06-15 | 2026/06/15 09:00 - 17:00 | Contractor A | Hot Work for Piping Repair | Plant 1 North Pit | Hot Work | JSA-001 |  | Очаква одобрение | Safety Manager A | Pending final check of fire extinguishers and watch
PT-2026-002 | 2026-06-15 | 2026/06/15 13:00 - 16:00 | Maintenance Dept | Rooftop Duct Inspection | Покрив | Work at Height | JSA-002 |  | Връзка / автоматично отразяване | Site Agent B | Harness usage confirmed
PT-2026-003 | 2026-06-16 | 2026/06/16 10:00 - 15:00 | Contractor B | Confined Space Drain Cleaning | Underground Pit | Confined Space | JSA-003 |  | Чернова | EHS Specialist C | Oxygen detector calibration check
PT-2026-004 | 2026-06-16 | 2026/06/16 08:30 - 12:00 | Excavation Partner | Excavation Verification for Drain Pipes | Exterior Area | Изкопни работи | JSA-004 |  | Одобрени заявки | Construction Manager D | Buried utilities map verified

## JSA Sheet
JSA Sheet
Break down tasks into steps to record hazards, initial risks, safety controls, and residual risks. Probability (L) and Severity (S) are rated from 1 to 5.
JSA Ref ID | Work Step / Sequence | Potential Hazard (Event) | Initial Risk L | Initial Risk S | Initial Risk Score R | Initial Evaluation Rank | Safety Measures (Control Actions) | Residual Risk L | Residual Risk S | Residual Risk Score R | Residual Evaluation Rank | Person in Charge
JSA-001 | Protection around piping | Sparks scatter to combustibles causing fire | 3 | 5 |  |  | Remove combustibles, install fire blankets, place 2 fire extinguishers | 1 | 5 |  |  | Alex Morgan
JSA-001 | Grinder cutting | Cutting dust enters eyes causing injury | 3 | 3 |  |  | Wear safety goggles and flame-resistant gloves, assign hot work watch | 1 | 3 |  |  | Jordan Lee
JSA-002 | Ascending/descending to roof | Falls during ascent/descent | 2 | 5 |  |  | Inspect ladders, use full-body harness with double lanyards | 1 | 5 |  |  | Taylor Reed
JSA-003 | Confined space entry (culvert) | Loss of consciousness due to oxygen deficiency | 2 | 5 |  |  | Measure oxygen level, set up forced ventilation, assign watch, confirm rescue plan | 1 | 5 |  |  | Casey Brooks

## Permit Checklist
Permit Checklist
Required checklist items before commencing hot work, work at height, confined space, or excavation. Select 'Yes / No / N/A' for each result.
Check ID | Work Permit Type | Елемент за инспекция | Резултат от проверка | Verified By | Verification Date/Time
CHK-001 | Hot Work | Remove nearby combustibles and shield the spark area | Yes | Jordan Lee | 2026-06-15 08:45
CHK-002 | Hot Work | Place fire extinguishers near the work area and ensure they are functional | Yes | Jordan Lee | 2026-06-15 08:48
CHK-003 | Work at Height | Wear full-body safety harness and verify hook anchorage point | Yes | Taylor Reed | 2026-06-15 12:40
CHK-004 | Confined Space | Perform measurements for oxygen and hydrogen sulfide concentrations | Не е приложимо | Casey Brooks | 2026-06-15 13:05
CHK-005 | Изкопни работи | Verify underground utilities map against local markings | Yes | Riley Carter | 2026-06-16 08:10

## Матрица на риска
Матрица на риска
Determines evaluation rank from Risk Value (L x S). The JSA Sheet references the threshold table on the right for risk ranking.
S\L | 1 | 2 | 3 | 4 | 5 | Min Risk Score | Evaluation Rank
1 | Управление | Управление | Управление | Управление | Управление | 1 | Управление
2 | Управление | Управление | Управление | Управление | Управление | 5 | Управление
3 | Управление | Управление | Управление | Управление | Управление | 10 | Управление
4 | Управление | Управление | Управление | Управление | Very High | 17 | Very High
5 | Управление | Управление | Управление | Very High | Very High
Evaluation Criteria
Low: Standard controls are sufficient.
Medium: Verify additional controls; supervisor approval required.
High: Revise methods/isolation controls; EHS approval required.
Very High: Work prohibited. Redesign risk mitigation controls.

## Worker List
Worker List
Roster for workers assigned to high-risk activities. Keep safety training dates and validity status updated.
Employee/Worker ID | Name | Company / Department | Qualification | Safety Training Date | Validity Status
W-001 | Alex Morgan | Maintenance Dept | Arc Welding | 2026-04-10 | Валиден
W-002 | Jordan Lee | Contractor A | Fire Watcher | 2026-05-12 | Валиден
W-003 | Taylor Reed | Engineering Dept | Full-body Harness | 2025-08-20 | Валиден
W-004 | Casey Brooks | EHS Dept | Oxygen Deficiency Prev. | 2024-06-18 | Изтекъл

## History Log
History Log
Archive past completed work permits to document findings, corrective actions, and lessons learned.
History ID | Permit No. | Дата на завършване | Job Title | Управление | Work Type | Final Status | Одобряващ | Продължителност | Deficiencies / Findings | Corrective Actions | Lessons / Prevention
HIS-001 | PT-2026-000 | 2026-06-10 | Warehouse Lighting Replacement | Warehouse | Work at Height | Централен строителен проект | Site Agent B | 2.5h | Insufficient barricading around the stepladder | Placed additional safety cones | Clearly separate pedestrian lanes from work zones
HIS-002 | PT-2026-00A | 2026-06-12 | Welding Repair | Plant 2 | Hot Work | Централен строителен проект | Safety Manager A | 4.0h | Missing entries in hot work watch log | Added record fields to the checklist | Include post-job inspection in the permit closure conditions

## Основни настройки
Основни настройки
Manages options used in dropdown lists across sheets. Add new values as needed.
Work Type | Статус на одобрение | Check Result | Местоположение | Qualification | Valid Status | Permit Type | Risk L/S | Одобряващ
Hot Work | Чернова | Yes | Plant 1 | Скеле | Валиден | Hot Work | 1 | Safety Manager A
Work at Height | Очаква одобрение | No | Plant 2 | Oxygen Deficiency Prev. | Изтекъл | Work at Height | 2 | Site Agent B
Confined Space | Одобрени заявки | Не е приложимо | Покрив | Arc Welding |  | Confined Space | 3 | EHS Specialist C
Изкопни работи | Връзка / автоматично отразяване |  | Underground Pit | Rigging / Slinging |  | Изкопни работи | 4 | Site Manager D
Други | Централен строителен проект |  | Warehouse | Aerial Lift |  |  | 5
| Suspended |  | Exterior Area | Organic Solvent
Full-body Harness