## Instructions
LEC Risk Assessment Auto Scoring Guide
Manage hazard identification, automatic risk ranking, control assignment, and corrective action tracking in one workbook.
Template Overview
This template automatically calculates the risk score D for each hazard using the LEC method (Likelihood × Exposure × Consequence). It displays the risk level and recommended controls based on the D score, and tracks progress for action items in the Corrective Action Log.
4-Step Workflow
Step | Action | Details
1 | [Verify Criteria] | Review and adjust your company's L, E, and C coefficients and thresholds in the 'Master Settings' sheet.
2 | [Register Hazards] | Enter process names, hazards, and responsible departments in the 'Risk Assessment Log' sheet.
3 | [Auto-Calculate] | Select L, E, and C from the dropdowns; the D score (= L × E × C), risk level, and recommended controls will populate automatically.
4 | [Track Actions] | Enter corrective action plans for items requiring mitigation and track their progress in the 'Corrective Action Log'.
Cell Color Legend
Category | Color | Usage
Input Cell | #E6F0FA | Cells for free text entry, such as dates, task names, hazards, and planned corrective actions.
Select (Dropdown) Cell | #EAF7EA | Cells to select from master lists, such as responsible department, L, E, C, and status.
Auto-Calculation / Formula Cell | White | Cells populated automatically, such as D score, risk level, recommended controls, and lookup values.
Risk Level Legend
D Score Range | Risk Level | Recommended Controls
D >= 320 | Critical Risk | Stop operations immediately. Top priority corrective action.
160 <= D < 320 | Major Risk | Prompt corrective action required. Responsible department to implement.
70 <= D < 160 | Moderate Risk | Plan corrective actions and revise procedures.
20 <= D < 70 | Low Risk | Monitor or consider improvements.
D < 20 | Acceptable Risk | Maintain current controls. No specific action required.
Operation Notes
For risks with a D score of Moderate or higher, you must update the planned corrective actions and the Corrective Action Log. If you need to modify departments or thresholds, edit the 'Master Settings' sheet first to update the dropdowns and formulas.

## Dashboard
Dashboard
Aggregates and visualizes hazards registered in the Risk Assessment Log in real time.
Total Hazards |  |  | Actions Required |  |  | Open Actions
Registered hazard count |  |  | Moderate risk and above |  |  | Not started or in progress
Summary by Risk Level |  |  |  | Summary by Department
Risk Level | Count | Share |  | Responsible Department | Total Count | Moderate & Above | Open | Highest D score
Critical Risk |  |  |  | Production Dept
Major Risk |  |  |  | Engineering Dept
Moderate Risk |  |  |  | EHS Dept
Low Risk |  |  |  | Administration Dept
Acceptable Risk |  |  |  | Logistics Dept

## Risk Assessment Log
LECリスク評価表
Select likelihood L, exposure E, and consequence C to calculate D score, risk level, and recommended controls automatically.
No. | Assessment Date | Process / Task | Hazard / Risk Description | Responsible Department | 発生可能性 L | 暴露頻度 E | 結果の重大性 C | Risk Score D | Risk Level | Recommended Controls | Planned Corrective Actions | Action Status
1 | 2026/06/01 | Welding operations | Fire or burns from sparks | Production Dept | 6 | 6 | 15 |  |  |  | Install fire blankets and assign fire watch | In progress
2 | 2026/06/02 | Rooftop inspection | Fall from ladder | EHS Dept | 3 | 3 | 15 |  |  |  | Retrain on harness use and add checklist | Not started
3 | 2026/06/03 | Forklift transport | Collision with pedestrian or caught-between | Logistics Dept | 6 | 6 | 7 |  |  |  | Repaint pedestrian lanes and install safety mirrors | In progress
4 | 2026/06/04 | Chemical storage | Skin irritation or inhalation from chemical spill | Engineering Dept | 1 | 2 | 3 |  |  |  | Post SDS and organize PPE cabinet | Completed

## Corrective Action Log
Corrective Action Log
Track corrective action plans and closure status for risks requiring mitigation.
Ref No. | Hazard / Risk Description | Corrective Action Details | Action Owner | Target Date | Completion Date | Verified By | Status | Remarks
1 |  | Verify hot work area during pre-start KY and remove combustibles | Yamada | 2026/06/20 |  | Sato | In progress | Added staffing standards for fire watch
2 |  | Post ladder safety rules and review inspection logs daily | Suzuki | 2026/06/25 |  | Tanaka | Not started | Training materials prepared by EHS Dept
3 |  | Repaint pedestrian safety lanes and install blind spot mirrors at intersections | Takahashi | 2026/06/18 |  | Sato | In progress | Layout options under review by Logistics Dept
4 |  | Update SDS postings and PPE cabinet labeling | Nakamura | 2026/06/10 | 2026/06/09 | Sato | Completed | Effectiveness check planned during monthly audit

## Master Settings
Master Settings
Define LEC evaluation parameters, risk level thresholds, department names, and statuses.
Likelihood L (Likelihood) |  |  | Exposure E (Exposure) |  |  | Consequence C (Consequence)
Coefficient | Description | English | Coefficient | Description | English | Coefficient | Description | Addendum | English
10 | Almost certain | expected | 10 | Continuous (or several times per day) | continuous / many times per day | 100 | Catastrophe | Multiple fatalities | catastrophe
6 | Quite possible | quite possible | 6 | Daily (or several times per week) | daily / several times per week | 40 | Disaster | Fatalities | disaster
3 | Unusual but possible | unusual but possible | 3 | Weekly (or several times per month) | weekly / several times per month | 15 | Very serious | One fatality or serious injury | very serious
1 | Only remotely possible | only remotely possible | 2 | Monthly (or several times per year) | monthly / several times per year | 7 | Serious | Serious injury | serious
0.5 | Conceivable but improbable | conceivable but improbable | 1 | Yearly | yearly | 3 | Important | Lost time injury | important
0.2 | Practically impossible | practically impossible | 0.5 | Very rare | very rare | 1 | Minor | Minor injury / first aid | minor
0.1 | Virtually impossible | virtually impossible
Risk Level Thresholds (D = L × E × C) |  |  |  |  | Department List |  | Status List
Lower D Limit | Upper D Limit | Risk Level | Recommended Controls |  | Responsible Department |  | Status
0 | 19 | Acceptable Risk | Maintain current controls. No specific action required. |  | Production Dept |  | Not started
20 | 69 | Low Risk | Monitor or consider improvements. |  | Engineering Dept |  | In progress
70 | 159 | Moderate Risk | Plan corrective actions and revise procedures. |  | EHS Dept |  | Completed
160 | 319 | Major Risk | Prompt corrective action required. Responsible department to implement. |  | Administration Dept
320 | and above | Critical Risk | Stop operations immediately. Top priority corrective action. |  | Logistics Dept