## Dashboard
New Hire 30-Day Plan Dashboard
Automatically summarizes the schedule plan, training checklist, and mentor feedback for weekly reviews and the Day 30 check.
Schedule Tasks |  | Schedule Completion | Training Completion |  | Delayed or Blocked Items | Day 30 Score
Weekly Completion Rate |  |  | Training Category Completion |  |  | Items to Watch
Week | Completion Rate | Delayed Count | Item | Completion Rate | Delayed Count | Source | Item
1 |  |  | Culture Fit |  |  | Schedule Plan | 30-day plan is closed
2 |  |  | Policy Process |  |  | Training Checklist | Ticket System, SLA, and Service Levels
3 |  |  | Systems and Tools |  |  | Mentor Feedback | Day 30 Score
4 |  |  | Compliance
Role Basics
Process Skills

## Guide
New Hire 30-Day Training and Mentoring Plan Template
Designed for service operations, customer support, retail, fulfillment, and back-office roles. HR, the manager, the mentor, and the new hire maintain it together.
How to Use
No. | Item
1 | Enter the company, team, role, start date, manager, mentor, work mode, and business scenario in Settings.
2 | Confirm the four-week stage goals, key deliverables, and acceptance rules in the 30-Day Overview.
3 | Adjust daily training, practice work, and mentor actions in the Schedule Plan, then track progress with the status dropdown.
4 | Select general and scenario-specific modules in the Training Checklist, then record completion, scores, and evidence links.
5 | Use Mentor Feedback to record 1:1s, weekly reviews, and the Day 30 assessment, then turn them into 60/90-day actions.
6 | Use the Dashboard to review completion rates, delayed items, training progress, scores, and summary charts.
Template Maintenance Notes
Item | Why
Lock the required items first, then add role-specific items. | This prevents the first week from becoming overloaded.
Every delayed item must include the blocker reason. | The manager and mentor can decide what support is needed.
Keep evidence links after the Day 30 review. | They make the 60/90-day follow-up easier to continue.

## Settings
Settings
Changing the inputs on this sheet updates schedule dates, the 30-day overview, and the dashboard. The option library can be adapted to company rules.
Field | Input or Selection | Description | Status | Priority | Owner | Business Scenario
Company | Northstar Services Inc. | Company | Not Started | High | HR | General
Department/Team | Service Operations |  | In Progress | Medium | Manager | Sales/BD
New Hire | John Miller |  | Completed | Low | Mentor | Customer Support
Role | Service Operations Associate |  | Delayed |  | IT/Admin | Engineering/Technology
Start Date | 2026-05-01 |  |  |  | New Hire | Product/Project
Manager | Sarah Lee |  |  |  |  | Operations/Supply Chain
Mentor | Emily Carter |  |  |  |  | Retail/Frontline Service
Work Mode | Hybrid |  |  |  |  | Manager/Transfer
Business Scenario | Customer Support
Probation Days | 90
Day 30 Review Date
30-Day Main Goal | Complete culture, system, process, and basic practice learning so the new hire can handle low-risk work with limited support.
Outcome Measurement Rule | Plan completion rate, training pass rate, mentor score, first deliverable quality, and no compliance exceptions.

## 30-Day Overview
30-Day Overview and Stage Goals
Organizes the first month into four stages with goals, deliverables, checkpoints, and key metrics.
Company |  | New Hire |  | Role | Start Date | Business Scenario
Schedule Completion |  | Training Completion |  | Delayed or Blocked Items | Day 30 Score | Day 30 Review Date
30-Day Main Goal
Outcome Measurement Rule
Four-Week Stage Goals
Week | 30-Day Main Goal | Key Deliverables | Acceptance Standard
Week 1: Arrival and Integration | Complete admin, IT, policy, team, and role basics | Onboarding checklist, system access, draft 30-day goals | Are goals aligned and access ready?
Week 2: Role Training | Learn SOPs, system use, quality standards, and working interfaces | Learning notes, task outputs, review materials | Can low-risk work be done under supervision?
Week 3: Scenario Practice | Practice standard tasks, exception cases, and cross-team communication | Practice evidence and exception exercise notes | Can exceptions be identified and escalated?
Week 4: Independent Handling | Complete standard work independently and prepare the Day 30 package | First deliverable, knowledge notes, review materials | Can standard work be owned and reviewed?

## Schedule Plan
30-Day Schedule Plan
Tracks daily learning, practice tasks, mentor actions, and acceptance results. Adjust the day sequence for calendar days or working days.
Day | Week | Date | Stage | Daily Theme | Morning Core Action | Afternoon Practice Task | Mentor Action | Materials or System Needed | Acceptance Standard or Output | Owner | Status | Priority | Risk or Blocker | Evidence or Note | Planned Completion Date | Adjustment Note
1 |  |  | Week 1 Arrival and Integration | Welcome and Admin/IT Setup | Welcome meeting, team introductions, collaboration rules | Welcome meeting, team introductions, collaboration rules | Review, demonstrate, and answer questions | SOP, system, checklist | Accounts and devices are ready | HR | Completed | High
2 |  |  | Week 1 Arrival and Integration | Culture and Policies | Study policies and record key questions | Study policies and record key questions | Review, demonstrate, and answer questions | SOP, system, checklist | Three key questions are recorded | Manager | Completed | Medium
3 |  |  | Week 1 Arrival and Integration | Role Scope and 30-Day Goal Alignment | Confirm goals, deliverables, and priorities | Confirm goals, deliverables, and priorities | Review, demonstrate, and answer questions | SOP, system, checklist | Draft personal 30-day goals | Mentor | In Progress | Low
4 |  |  | Week 1 Arrival and Integration | Tools and Information Security | Log in to core systems and verify access | Log in to core systems and verify access | Review, demonstrate, and answer questions | SOP, system, checklist | Login and security confirmation are complete | IT/Admin | In Progress | High
5 |  |  | Week 1 Arrival and Integration | Compliance, Safety, and Basic Process | Learn compliance and safety requirements | Learn compliance and safety requirements | Review, demonstrate, and answer questions | SOP, system, checklist | Compliance quiz or confirmation is complete | New Hire | Not Started | Medium
6 |  |  | Week 1 Arrival and Integration | Business Flow Introduction | Observe typical business handling | Observe typical business handling | Review, demonstrate, and answer questions | SOP, system, checklist | One-page business understanding note | HR | Not Started | Low
7 |  |  | Week 1 Arrival and Integration | Week 1 Review | Organize questions and confirm next-week focus | Organize questions and confirm next-week focus | Review, demonstrate, and answer questions | SOP, system, checklist | Week 1 review and next-week plan | Manager | Not Started | High
8 |  |  | Week 2 Role Training | Core SOP Learning | Learn the main flow and role split | Learn the main flow and role split | Review, demonstrate, and answer questions | SOP, system, checklist | Can explain standard work and risks | Mentor | Not Started | Medium
9 |  |  | Week 2 Role Training | System Practice and Data Rules | Practice system use and data rules | Practice system use and data rules | Review, demonstrate, and answer questions | SOP, system, checklist | System operation exercise is complete | IT/Admin | Not Started | Low
10 |  |  | Week 2 Role Training | Shadowing | Observe the mentor handling real work | Observe the mentor handling real work | Review, demonstrate, and answer questions | SOP, system, checklist | Observation notes and question list | New Hire | Not Started | High
11 |  |  | Week 2 Role Training | Low-Risk Task Practice | Complete one standard task under supervision | Complete one standard task under supervision | Review, demonstrate, and answer questions | SOP, system, checklist | Low-risk task passes review | HR | Not Started | Medium
12 |  |  | Week 2 Role Training | Collaboration Routine | Send one collaboration request | Send one collaboration request | Review, demonstrate, and answer questions | SOP, system, checklist | Collaboration record is reviewed | Manager | Not Started | Low
13 |  |  | Week 2 Role Training | Week 2 Assessment | Assess process, system, and collaboration capability | Assess process, system, and collaboration capability | Review, demonstrate, and answer questions | SOP, system, checklist | Week 2 assessment is complete | Mentor | Not Started | High
14 |  |  | Week 2 Role Training | Low-Risk Task Ownership | Take one real low-risk task | Take one real low-risk task | Review, demonstrate, and answer questions | SOP, system, checklist | Standard task meets requirements | IT/Admin | Not Started | Medium
15 |  |  | Week 3 Scenario Practice | Exception Case Exercise | Simulate one exception case | Simulate one exception case | Review, demonstrate, and answer questions | SOP, system, checklist | Can judge escalation criteria | New Hire | Not Started | Low
16 |  |  | Week 3 Scenario Practice | Metrics and Report Reading | Analyze one metric or report | Analyze one metric or report | Review, demonstrate, and answer questions | SOP, system, checklist | Can explain key metric meaning | HR | Not Started | High
17 |  |  | Week 3 Scenario Practice | Knowledge Capture | Capture an FAQ or operation note | Capture an FAQ or operation note | Review, demonstrate, and answer questions | SOP, system, checklist | Knowledge entry is complete | Manager | Not Started | Medium
18 |  |  | Week 3 Scenario Practice | Cross-Team Collaboration Exercise | Run a mock cross-team request | Run a mock cross-team request | Review, demonstrate, and answer questions | SOP, system, checklist | Cross-team communication record is complete | Mentor | Not Started | Low
19 |  |  | Week 3 Scenario Practice | Week 3 Review | Review task evidence and gaps | Review task evidence and gaps | Review, demonstrate, and answer questions | SOP, system, checklist | Week 3 review is complete | IT/Admin | Not Started | High
20 |  |  | Week 3 Scenario Practice | Independent Standard Work | Submit progress and results at checkpoints | Submit progress and results at checkpoints | Review, demonstrate, and answer questions | SOP, system, checklist | Standard work is completed independently | New Hire | Not Started | Medium
21 |  |  | Week 3 Scenario Practice | Quality and Correction | Fix errors and explain the reason | Fix errors and explain the reason | Review, demonstrate, and answer questions | SOP, system, checklist | Quality and correction speed meet standard | HR | Not Started | Low
22 |  |  | Week 4 Independent Handling | Improvement Suggestions | Submit one to three small improvements | Submit one to three small improvements | Review, demonstrate, and answer questions | SOP, system, checklist | Actionable improvement suggestions | Manager | Not Started | High
23 |  |  | Week 4 Independent Handling | Day 30 Evidence Package | Organize training records and practice evidence | Organize training records and practice evidence | Review, demonstrate, and answer questions | SOP, system, checklist | Day 30 evidence package | Mentor | Not Started | Medium
24 |  |  | Week 4 Independent Handling | Day 30 Review | Confirm outcomes, scores, and risks | Confirm outcomes, scores, and risks | Review, demonstrate, and answer questions | SOP, system, checklist | Day 30 review and action plan | IT/Admin | Not Started | Low
25 |  |  | Week 4 Independent Handling | 60/90-Day Action Plan | Create follow-up growth actions | Create follow-up growth actions | Review, demonstrate, and answer questions | SOP, system, checklist | Next goals and owners are clear | New Hire | Not Started | High
26 |  |  | Week 4 Independent Handling | Handover and Archive | Archive evidence links and learning notes | Archive evidence links and learning notes | Review, demonstrate, and answer questions | SOP, system, checklist | Follow-up materials are ready | HR | Not Started | Medium
27 |  |  | Week 4 Independent Handling | Team Sharing | Turn questions into team knowledge | Turn questions into team knowledge | Review, demonstrate, and answer questions | SOP, system, checklist | Team knowledge base is updated | Manager | Not Started | Low
28 |  |  | Week 4 Independent Handling | Buffer Slot | Close unfinished items | Close unfinished items | Review, demonstrate, and answer questions | SOP, system, checklist | Delayed items have support actions | Mentor | Not Started | High
29 |  |  | Week 4 Independent Handling | Management Confirmation | Confirm next authority boundary | Confirm next authority boundary | Review, demonstrate, and answer questions | SOP, system, checklist | Next authority is clear | IT/Admin | Not Started | Medium
30 |  |  | Week 4 Independent Handling | Plan Close | Close the 30-day plan | Close the 30-day plan | Review, demonstrate, and answer questions | SOP, system, checklist | 30-day plan is closed | New Hire | Not Started | Low

## Training Checklist
Training Checklist and Assessment Record
Covers general onboarding and service-operations modules, with role relevance driven by the business scenario in Settings.
ID | Training Topic | Category | Scenario Fit | Applies to Current Role | Required or Elective | Target Capability | Deliverable or Assessment Method | Owner | Suggested Start Day | Planned Completion Day | Score or Pass Rate | Status | Evidence Link or Record | Risk Note | Response Suggestion | Note
T01 | Company Culture, Organization, and Values | Culture Fit | General |  | Required | Understand company goals and key contacts | Learning note / check | HR | 1 | 7 |  | Not Started
T02 | Handbook, Attendance, Benefits, and Expenses | Policy Process | General |  | Required | Understand basic policies and support paths | Learning note / check | Manager | 2 | 8 |  | Not Started
T03 | IT Accounts, Devices, Access, and Collaboration Tools | Systems and Tools | General |  | Required | Use office and approval tools independently | Learning note / check | Mentor | 3 | 9 |  | Not Started
T04 | Information Security, Confidentiality, and Data Access | Compliance | General |  | Required | Identify data access boundaries | Learning note / check | IT/Admin | 4 | 10 |  | Not Started
T05 | Role Scope, RACI, and Key Metrics | Role Basics | General |  | Required | Clarify responsibilities and success standards | Learning note / check | New Hire | 5 | 11 |  | Not Started
T06 | Core SOPs and Quality Standards | Process Skills | General |  | Required | Explain standard work using the SOP | Learning note / check | HR | 6 | 12 |  | Not Started
T07 | Customer or User Privacy and Sensitive Data Handling | Compliance | General |  | Required | Handle personal information correctly | Learning note / check | Manager | 7 | 13 |  | Not Started
T08 | Ticket System, SLA, and Service Levels | Customer Support | Customer Support |  | Required | Understand response timelines and escalation | Learning note / check | Mentor | 8 | 14 |  | Not Started
T09 | Knowledge Search and Issue Diagnosis | Knowledge Management | Customer Support |  | Required | Find answers and capture recurring questions | Learning note / check | IT/Admin | 9 | 15 |  | Not Started
T10 | Complaint Escalation and De-escalation Wording | Customer Support | Customer Support |  | Required | Use standard wording for complaints | Learning note / check | New Hire | 10 | 16 |  | Not Started
T11 | Cross-Team Collaboration and Escalation | Collaboration | General |  | Required | Know when to share and escalate | Learning note / check | HR | 11 | 17 |  | Not Started
T12 | Business Metrics and Report Reading | Business Understanding | General |  | Required | Understand quality, time, and cost metrics | Learning note / check | Manager | 12 | 18 |  | Not Started
T13 | Low-Risk Standard Task Practice | Practice | General |  | Required | Complete standard work by process | Learning note / check | Mentor | 13 | 19 |  | Not Started
T14 | Exception Case Exercise | Risk Management | General |  | Required | Identify exceptions and escalate correctly | Learning note / check | IT/Admin | 14 | 20 |  | Not Started
T15 | Knowledge Capture and Experience Review | Knowledge Management | General |  | Elective | Turn questions into team assets | Learning note / check | New Hire | 15 | 21 |  | Not Started
T16 | First Business Deliverable | Business Output | General |  | Required | Create the first business deliverable | Learning note / check | HR | 16 | 22 |  | Not Started
T17 | Day 30 Outcome Review | Feedback | General |  | Required | Review outcomes and gaps | Learning note / check | Manager | 17 | 23 |  | Not Started
T18 | 60/90-Day Action Plan | Feedback | General |  | Required | Create a follow-up growth plan | Learning note / check | Mentor | 18 | 24 |  | Not Started

## Mentor Feedback
Mentor Feedback and Day 30 Assessment
Records key 1:1s, weekly reviews, capability scores, and follow-up actions so the manager and mentor can close the loop.
Mentor/Manager Check-in Plan
Milestone | Date | Meeting Theme | Suggested Agenda | Owner | Status | Feedback Summary | Next Action
Day 1 |  | Welcome and Admin/IT Setup | Accounts and devices are ready | HR | Completed
Day 3 |  | Role Scope and 30-Day Goal Alignment | Compliance quiz or confirmation is complete | Manager | Not Started
Day 5 |  | Week 1 Review | System operation exercise is complete | Mentor | Not Started
Day 7 |  | Week 1 Review | Week 2 assessment is complete | IT/Admin | Not Started
Day 14 |  | Week 2 Assessment | Knowledge entry is complete | New Hire | Not Started
Day 21 |  | Week 3 Review | Quality and correction speed meet standard | HR | Not Started
Day 30 |  | Day 30 Review | Next goals and owners are clear | Manager | Not Started
Day 30 Score
Dimension | Weight | Self Score (1-5) | Mentor Score (1-5) | Manager Score (1-5) | Weighted Score | Acceptance Standard | Next Action
Culture Fit | 10 | 3 | 3 | 3 |  | Understand company goals and key contacts
Process Skills | 20 | 3 | 3 | 3 |  | Explain standard work using the SOP
Systems and Tools | 20 | 3 | 3 | 3 |  | Use office and approval tools independently
Collaboration | 15 | 3 | 3 | 3 |  | Know when to share and escalate
Business Output | 25 | 3 | 3 | 3 |  | Create the first business deliverable
Follow-Up Action Plan | 10 | 3 | 3 | 3 |  | Complete culture, system, process, and basic practice learning so the new hire can handle low-risk work with limited support.
Follow-Up Action Plan
Item | Owner | Due Date | Status | Next Action
Next goals and owners are clear | Manager |  | Not Started | Create follow-up growth actions
Follow-up materials are ready | Mentor |  | Not Started | Archive evidence links and learning notes
Team knowledge base is updated | IT/Admin |  | Not Started | Turn questions into team knowledge
Day 30 Score

## Role Scenario Library
Role Scenario Library: Scenario Content for the Plan
Select focus tasks, systems, risks, and metrics by business type so the template can support multiple roles and teams.
Business Scenario | Typical Roles | First 30-Day Focus | Required Systems or Tools | Key Risks | Recommended Mentor or Partners | Sample Metrics | Task Example to Copy
General | Functional, operations, admin, HR, and support roles | Culture, role scope, systems, SOPs, and collaboration routines | Chat, email, workflow, knowledge base, approval system | Missing access, unclear ownership, information overload | HRBP, manager, mentor, IT/Admin | Plan completion, training pass rate, mentor score, risk count | Map role RACI and create a one-page business understanding note
Sales/BD | Sales rep, account manager, channel manager | Value proposition, customer profile, CRM, follow-up rhythm, quote approval | CRM, quoting, contract, product library | Incomplete customer data, over-promising, quoting errors | Sales manager, senior seller, presales/legal | CRM record completeness, mock visit score, first lead follow-up quality | Complete a customer follow-up simulation and submit a visit review
Customer Support | Support specialist, after-sales support, ticket handler | SLA, wording, ticket flow, complaint escalation, knowledge search | Ticketing system, knowledge base, phone or online support | Late response, inconsistent wording, delayed escalation | Support lead, quality reviewer, senior support teammate | Ticket accuracy, SLA attainment, quality score | Handle three low-risk tickets under supervision and complete a review
Engineering/Technology | Developer, tester, operations engineer, data engineer | Development environment, coding standards, branching, CI/CD, secure development | Code repository, CI/CD, issue tracker, monitoring | Access and environment issues, release risk, security gaps | Technical mentor, architect, test/operations partner | PR quality, defect cycle time, documentation completeness | Complete one code review workflow or fix one low-risk defect
Product/Project | Product manager, project manager, delivery manager | Requirements process, user stories, scheduling, risk list, acceptance criteria | Requirements/project tools, prototyping tools, meeting notes | Unclear scope, missed requirements, late risk discovery | Product owner, project manager, business stakeholder | Requirement document quality, risks identified, action closure rate | Break down one requirement and write acceptance criteria and risks
Operations/Supply Chain | Operations associate, supply chain, fulfillment, data operations | SOPs, metric definitions, exception handling, reporting, cross-team work | ERP, WMS, BI, scheduling or fulfillment system | Bad metric definitions, delayed exception escalation, fulfillment variance | Operations manager, data analyst, warehouse/support partners | Report accuracy, exception cycle time, SOP adherence | Analyze one operations report and propose exception hypotheses
Retail/Frontline Service | Store associate, cashier, sales floor, field service | Service standards, POS, display, inventory, returns, complaints | POS, membership, inventory, store SOP | Cashier errors, complaint escalation, inventory mismatch | Store manager, senior associate, area supervisor | Service score, transaction accuracy, stock count accuracy | Complete one service simulation and POS exercise
Manager/Transfer | New manager, internal promotion, team lead | Team goals, management rhythm, performance feedback, authority boundaries, cross-team work | Performance system, project board, meeting cadence, team dashboard | Too much or too little authority, late feedback, goal mismatch | Senior manager, HRBP, peer managers | 1:1 completion, goal alignment, team risk list | Create a 30-day team operating rhythm and run a mock 1:1